## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR | Ramnagar-I | Midnapore Mechanical | FATEPUR AND ADJOINING MOUJAS PWSS | SM/13687 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for FATEPUR and ADJOINING MOUJAS, Block ¿ Ramnagar I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division | ORD/001673/2022-2023 | 570/W/MMD | 20/03/2023 | 09/09/2024 | DEY ENTERPRISE | 11.98 | 10.88 | 90.83 | 100
2 | PURBA MEDINIPUR | Ramnagar-I | Tamluk Division | FATEPUR AND ADJOINING MOUJAS PWSS | SM/13687 | New | Material Requisition To Resource Division |  |  | RTOR000269/2022-2023 | 2697/TD | 06/02/2023 | 06/02/2023 | Resource Division | 4.51 | 0 | 0 | 0
3 | PURBA MEDINIPUR | Ramnagar-I | Midnapore Mechanical | FATEPUR AND ADJOINING MOUJAS PWSS | SM/13687 | New | Fatepur W/S scheme PH-I Application no.-2004511512 ref.-204147631 |  |  | BILL/03193/2023-2024 | BP-2023-24-468 | 27/12/2023 | 27/12/2023 | WBSEDCL | 0.86 | 0 | 0 | 0
4 | PURBA MEDINIPUR | Ramnagar-I | Tamluk Division | FATEPUR AND ADJOINING MOUJAS PWSS | SM/13687 | New | Drum Sheet walling, road restoration for distribution pipe line( for FHTC) & Accommodate FHTC (82 Nos) under JJM with allied work for FATEPUR PWSS within Ramnagar-I Block under Digha Sub-Division of Tamluk Division , PHED , Purba Medinipur | Assistant Engineer |  | ORD/000466/2024-2025 | 3722/TD | 04/12/2024 | 03/01/2025 | MAITY CONSTRUCTION | 14.16 | 0 | 0 | 0
5 | PURBA MEDINIPUR | Ramnagar-I | Tamluk Division | FATEPUR AND ADJOINING MOUJAS PWSS | SM/13687 | New | Material Requisition To Resource Division |  |  | RTOR000132/2023-2024 | 107/TD | 05/01/2024 | 05/01/2024 | Resource Division | 2.32 | 0 | 0 | 0
6 | PURBA MEDINIPUR | Ramnagar-I | Midnapore Mechanical | FATEPUR AND ADJOINING MOUJAS PWSS | SM/13687 | New | Fatepur W/S scheme TW-II Application No.-2004521 Ref.-204156067 |  |  | BILL/03363/2023-2024 | BP-2023-24-574 | 18/01/2024 | 18/01/2024 | WBSEDCL | 0.26 | 0 | 0 | 0
7 | PURBA MEDINIPUR | Ramnagar-I | Midnapore Mechanical | FATEPUR AND ADJOINING MOUJAS PWSS | SM/13687 | New | Quotation Bill for LOAD ENHANCEMENT at T/W NO-I Of FATEPUR W/S Scheme under MMD, PHE, Dte. Block- RAMANAGR-I, WBSEDCL SUPPLY OFFICE: DIGHA C.C.C. Ref. Memo No- 2005045654/QUOT/03 DT. 14-01-2025 Application NO- 2005045654 Application type-LOAD ENHANCEMENT Consumer Id- 204156067 |  |  | BILL/04114/2024-2025 | C022539974995 | 18/02/2025 | 18/02/2025 | WBSEDCL | 0.15 | 0 | 0 | 0
Total | [13 empty] | 34.24 | 10.88 | 31.78