## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR | Mahisadal | Tamluk Division | SAR BERYA AND ADJOINING MOUJAS PWSS | SM/13688 | New | Material Requisition To Resource Division |  |  | RTOR000137/2022-2023 | 2424/TD | 16/01/2023 | 16/01/2023 | Resource Division | 39.36 | 0 | 0 | 0
2 | PURBA MEDINIPUR | Mahisadal | Tamluk Division | SAR BERYA AND ADJOINING MOUJAS PWSS | SM/13688 | New | Ground water based Sar Berya Water Supply Scheme by providing Construction of Pump House, Boundary Wall, Laying of Rising main, Laying of Distribution pipe line and FHTC work within Mahishadal Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur.(Part-D) | Assistant Engineer | Junior Engineer | ORD/000808/2022-2023 | 3077/TD | 28/02/2023 | 26/09/2025 | J.M. CONSTRUCTION | 59.34 | 0 | 0 | 35
3 | PURBA MEDINIPUR | Mahisadal | Tamluk Division | SAR BERYA AND ADJOINING MOUJAS PWSS | SM/13688 | New | Ground water based Sar Berya Water Supply Scheme by providing Laying of Distribution pipe line and FHTC work within Mahishadal Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. (Part-F) | Assistant Engineer | Junior Engineer | ORD/000810/2022-2023 | 3079/TD | 28/02/2023 | 20/03/2023 | MADAN MOHAN MAITY | 36.48 | 0 | 0 | 100
4 | PURBA MEDINIPUR | Mahisadal | Midnapore Mechanical | SAR BERYA AND ADJOINING MOUJAS PWSS | SM/13688 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for SAR BERYA and ADJOINING MOUJAS, Block ¿ Mahishadal, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/001659/2022-2023 | 544/W/MMD | 20/03/2023 | 30/08/2024 | SOUMEN ELECTRIC | 21.56 | 0 | 0 | 100
5 | PURBA MEDINIPUR | Mahisadal | Tamluk Division | SAR BERYA AND ADJOINING MOUJAS PWSS | SM/13688 | New | Installation of display board at 2 (two) nos work site under Haldia Sub-Division of Tamluk Division, PHE Dte. (Phase-IV) [Sarberia PWSS & Urddhabmal PWSS] | Assistant Engineer | Junior Engineer | ORD/000832/2023-2024 | 620/HSD, | 21/12/2023 | 28/12/2023 | SANTANU PATTANAYAK | 0.42 | 0 | 0 | 100
6 | PURBA MEDINIPUR | Mahisadal | Tamluk Division | SAR BERYA AND ADJOINING MOUJAS PWSS | SM/13688 | New | Orientation Programme under Haldia Sub-Division of Tamluk Division, PHE Dte. (For 5 nos Blocks, i.e. - i) Sutahata Dev. Block, ii) Mahishadal Dev. Block, iii) Haldia Dev. Block, iv) Nandigram - I Dev. Block & v) Nandigram - II Dev. Block) | Assistant Engineer | Junior Engineer | ORD/001169/2023-2024 | 621/HSD, | 21/12/2023 | 23/12/2023 | TAPAN BERA | 0.94 | 0 | 0 | 100
7 | PURBA MEDINIPUR | Mahisadal | Tamluk Division | SAR BERYA AND ADJOINING MOUJAS PWSS | SM/13688 | New | Material Requisition To Resource Division |  |  | RTOR000170/2023-2024 | 112/TD | 05/01/2024 | 05/01/2024 | Resource Division | 5.39 | 0 | 0 | 0
8 | PURBA MEDINIPUR | Mahisadal | Tamluk Division | SAR BERYA AND ADJOINING MOUJAS PWSS | SM/13688 | New | Ground water based Sar Berya Water Supply Scheme by providing Construction of Pump House, Boundary Wall, Laying of Distribution pipe line and FHTC work within Mahishadal Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur.(Part-C) | Assistant Engineer | Junior Engineer | ORD/000807/2022-2023 | 3076/TD | 28/02/2023 | 30/03/2023 | PULAK KUMAR SAMANTA | 55.08 | 0 | 0 | 62
9 | PURBA MEDINIPUR | Mahisadal | Tamluk Division | SAR BERYA AND ADJOINING MOUJAS PWSS | SM/13688 | New | Ground water based Sar Berya Water Supply Scheme by providing Construction of R.C.C. Over Head Reservoir of capacity 100 cum and staging height 20.00 mtr. with allied work including Sub Soil Investigation within Mahishadal Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur.(Part-B) | Assistant Engineer | Junior Engineer | ORD/000450/2023-2024 | 1468/TD | 13/07/2023 | 28/08/2025 | JAGANNATH MAKAR | 80.39 | 0 | 0 | 3
10 | PURBA MEDINIPUR | Mahisadal | Tamluk Division | SAR BERYA AND ADJOINING MOUJAS PWSS | SM/13688 | New | Box Culvert at HW site & Construction of Retaining wall of ground water based Sarberia Water Supply Scheme within Mahisadal Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer |  | ORD/001241/2023-2024 | 1083/TD | 16/03/2024 | 25/04/2024 | JAGANNATH MAKAR | 13.42 | 0 | 0 | 0
11 | PURBA MEDINIPUR | Mahisadal | Tamluk Division | SAR BERYA AND ADJOINING MOUJAS PWSS | SM/13688 | New | Ground water based Sar Berya Water Supply Scheme by providing Construction of Pump House, Boundary Wall, Laying of Distribution pipe line and FHTC work within Mahishadal Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur.(Part-E) | Assistant Engineer | Junior Engineer | ORD/000809/2022-2023 | 3078/TD | 28/02/2023 | 20/05/2024 | R CONSTRUCTION | 42.52 | 0 | 0 | 100
Total | [13 empty] | 354.9 | 0 | 0