## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR | Ramnagar-II | Tamluk Division | KADUA AND IT'S ADJOINING MOUJAS | SM/13689 | New | Material Requisition To Resource Division |  |  | RTOR000216/2022-2023 | 2691/TD | 06/02/2023 | 06/02/2023 | Resource Division | 33.64 | 0 | 0 | 0
2 | PURBA MEDINIPUR | Ramnagar-II | Tamluk Division | KADUA AND IT'S ADJOINING MOUJAS | SM/13689 | New | Laying distribution pipe line, & Accommodate FHTC ( 70 Nos) under JJM with allied work for Kadua & Its Adjoining Mouzas Water Supply Scheme within Ramnagar-II Block under Digha Sub-Division of Tamluk Division , PHED , Purba Medinipur ( Part - E ) | Assistant Engineer | Junior Engineer | ORD/000483/2023-2024 | 1533/TD | 18/07/2023 | 07/08/2023 | HYDROTECH ASSOCIATES | 9.99 | 5.4 | 54.1 | 60
3 | PURBA MEDINIPUR | Ramnagar-II | Central Drilling | KADUA AND IT'S ADJOINING MOUJAS | SM/13689 | New | Hiring of Disel Driven Motor Cab ( BS-IV & Above) having contract carriage permit along with driver for the office of the Driller In Charge, CMSD-II (D) , CDD, P.H. Engineering Dte. | Driller In Charge | Junior Engineer | ORD/000190/2023-2024 | 264/CMSD-II(D) | 15/12/2023 | 15/06/2024 | DILIP KAR | 0.86 | 2.08 | 240.89 | 70
4 | PURBA MEDINIPUR | Ramnagar-II | Tamluk Division | KADUA AND IT'S ADJOINING MOUJAS | SM/13689 | New | Material Requisition To Resource Division |  |  | RTOR000146/2023-2024 | 125/TD | 05/01/2024 | 05/01/2024 | Resource Division | 13.24 | 0 | 0 | 0
5 | PURBA MEDINIPUR | Ramnagar-II | Midnapore Mechanical | KADUA AND IT'S ADJOINING MOUJAS | SM/13689 | New | Kadua W/S scheme PH-I Application No.-2004550666 Ref.-204181244 |  |  | BILL/03292/2023-2024 | BP-2023-24-539 | 11/01/2024 | 11/01/2024 | WBSEDCL | 2.97 | 0 | 0 | 0
6 | PURBA MEDINIPUR | Ramnagar-II | Midnapore Mechanical | KADUA AND IT'S ADJOINING MOUJAS | SM/13689 | New | Kadua W/S scheme PH-II Application No.-2004550634 Ref.-204181242 |  |  | BILL/03293/2023-2024 | BP-2023-24-538 | 11/01/2024 | 11/01/2024 | WBSEDCL | 2.76 | 0 | 0 | 0
7 | PURBA MEDINIPUR | Ramnagar-II | Tamluk Division | KADUA AND IT'S ADJOINING MOUJAS | SM/13689 | New | Laying distribution pipe line, Pump House, Boundary Wall & Accommodate FHTC ( 840 Nos) under JJM with allied work for Kadua & Its Adjoining Mouzas Water Supply Scheme within Ramnagar-II Block under Digha Sub-Division of Tamluk Division , PHED , Purba Medinipur (Part-B) | Assistant Engineer | Junior Engineer | ORD/000256/2023-2024 | 538/TD | 12/05/2023 | 12/02/2026 | GIRI CONSTRUCTION | 199.43 | 0 | 0 | 90
8 | PURBA MEDINIPUR | Ramnagar-II | Tamluk Division | KADUA AND IT'S ADJOINING MOUJAS | SM/13689 | New | Laying distribution pipe line, Pump House, Boundary Wall soil investigation, 300 Cum OHR ( Intze type with pile foundation ) & Accommodate FHTC ( 900Nos) under JJM with allied work for Kadua & Its Adjoining Mouzas Water Supply Scheme within Ramnagar-II Block under Digha Sub-Division of Tamluk Division , PHED , Purba Medinipur (Part-A) | Assistant Engineer | Junior Engineer | ORD/000628/2023-2024 | 2436/TD | 19/09/2023 | 26/06/2026 | BIDHAN MONDAL | 246.91 | 67.82 | 27.47 | 45
9 | PURBA MEDINIPUR | Ramnagar-II | Central Drilling | KADUA AND IT'S ADJOINING MOUJAS | SM/13689 | New | Continuation Hiring of Disel Driven Motor Cab ( BS-IV & Above) having contract carriage permit along with driver for the office of the Driller In Charge, CMSD-II (D) , CDD, P.H. Engineering Dte. | Driller In Charge | Junior Engineer | ORD/000032/2024-2025 | 124/CMSD-II(D) | 27/06/2024 | 26/12/2024 | DILIP KAR | 0.86 | 2.06 | 238.29 | 0
10 | PURBA MEDINIPUR | Ramnagar-II | Tamluk Division | KADUA AND IT'S ADJOINING MOUJAS | SM/13689 | New | Land development of 2nd T/W Site at Kadua & Its Adjoining Mouzas water Supply Scheme within Ramnagar-II BLOCK under Digha Sub-Division of Tamluk Division , PHE Dte. |  |  | ORD/000307/2024-2025 | 892/DSD | 02/09/2024 | 09/09/2024 | GIRI CONSTRUCTION | 1.85 | 0 | 0 | 0
11 | PURBA MEDINIPUR | Ramnagar-II | Central Drilling | KADUA AND IT'S ADJOINING MOUJAS | SM/13689 | New | Continuation Hiring of Disel Driven Motor Cab ( BS-IV & Above) having contract carriage permit along with driver for the office of the Driller In Charge, CMSD-II (D) , CDD, P.H. Engineering Dte. | Driller In Charge | Junior Engineer | ORD/000053/2024-2025 | 294/CMSD-II(D) | 30/12/2024 | 30/06/2025 | DILIP KAR | 0.86 | 2.08 | 240.76 | 0
12 | PURBA MEDINIPUR | Ramnagar-II | Tamluk Division | KADUA AND IT'S ADJOINING MOUJAS | SM/13689 | New | Laying distribution pipe line, & Accommodate FHTC (261Nos) under JJM with allied work for Kadua & Its Adjoining Mouzas Water Supply Scheme within Ramnagar-II Block under Digha Sub-Division of Tamluk Division , PHED , Purba Medinipur (Part-C ) | Assistant Engineer | Junior Engineer | ORD/000916/2022-2023 | 3553/TD | 29/03/2023 | 14/06/2025 | MRINAL KANTI PRADHAN | 84.53 | 69.26 | 81.94 | 100
13 | PURBA MEDINIPUR | Ramnagar-II | Tamluk Division | KADUA AND IT'S ADJOINING MOUJAS | SM/13689 | New | Laying distribution pipe line & Accommodate FHTC ( 81 Nos) under JJM with allied work for Kadua & Its Adjoining Mouzas Water Supply Scheme within Ramnagar-II Block under Digha Sub-Division of Tamluk Division , PHED , Purba Medinipur (Part - D ) | Assistant Engineer | Junior Engineer | ORD/000624/2023-2024 | 2363/TD | 12/09/2023 | 18/12/2024 | KESHOB ENTERPRISE | 19.96 | 15 | 75.14 | 100
Total | [13 empty] | 617.86 | 163.7 | 26.5