## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR | Contai-I | Tamluk Division | SAHAJADAPUR & IT'S ADJOINING MOUJAS PWSS | SM/13690 | New | Material Requisition To Resource Division |  |  | RTOR000166/2022-2023 | 2392/TD | 16/01/2023 | 16/01/2023 | Resource Division | 34.34 | 0 | 0 | 0
2 | PURBA MEDINIPUR | Contai-I | Tamluk Division | SAHAJADAPUR & IT'S ADJOINING MOUJAS PWSS | SM/13690 | New | Preparation of design based on soil test report and submission of drawing of foundation for construction of 100 cum RCC OHR at Sahajadapur PWSS at Contai-I Block under Tamluk Division,PHE Dte. |  |  | ORD/000881/2023-2024 | 203/TD | 10/01/2024 | 20/01/2024 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.96 | 0 | 0 | 0
3 | PURBA MEDINIPUR | Contai-I | Tamluk Division | SAHAJADAPUR & IT'S ADJOINING MOUJAS PWSS | SM/13690 | New | Material Requisition To Resource Division |  |  | RTOR000068/2024-2025 | 2977/TD | 12/09/2024 | 12/09/2024 | Resource Division | 3.28 | 0 | 0 | 0
4 | PURBA MEDINIPUR | Contai-I | Midnapore Mechanical | SAHAJADAPUR & IT'S ADJOINING MOUJAS PWSS | SM/13690 | New | Quotation for new service connection at TW-I of Sahajadapur ws scheme under MMD,PHE Dte. Ref. Application no-2004579826, CON ID-204204429, under PICHABONI CCC, Block-CONTAI-I |  |  | BILL/03655/2023-2024 | BP-2023-24-679 | 15/02/2024 | 15/02/2024 | WBSEDCL | 3.19 | 0 | 0 | 0
5 | PURBA MEDINIPUR | Contai-I | Tamluk Division | SAHAJADAPUR & IT'S ADJOINING MOUJAS PWSS | SM/13690 | New | Quotation Bill for New Service connection at T/W NO-II Of SAHAJADAPUR W/S Scheme under MMD, PHE, Dte. Block- CONTAI-I, WBSEDCL SUPPLY OFFICE: PICHABANI C.C.C. Ref. Memo No- 2004772844/QUOT/03 DT. 14-06-2024 Application NO- 2004772844 Application type-New connection Consumer Id- 204329286 |  |  | BILL/00591/2024-2025 | BP-2024-25-289 | 29/07/2024 | 29/07/2024 | WBSEDCL | 14.1 | 0 | 0 | 0
6 | PURBA MEDINIPUR | Contai-I | Midnapore Mechanical | SAHAJADAPUR & IT'S ADJOINING MOUJAS PWSS | SM/13690 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for SAHAJADAPUR and ADJOINING MOUJAS, Block ¿ Contai I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division | ORD/001657/2022-2023 | 543/W/MMD | 20/03/2023 | 30/04/2025 | SOUMEN ELECTRIC | 21.56 | 16.07 | 74.54 | 100
7 | PURBA MEDINIPUR | Contai-I | Tamluk Division | SAHAJADAPUR & IT'S ADJOINING MOUJAS PWSS | SM/13690 | New | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House & Providing Functional Household Tap Connection (32862 Nos), including 2 years Operation & Maintenance For 21 nos Pipe Water Supply Scheme within MOYNA AND CONTAI -I Block Under Tamluk Division PHE Dte. Under Purba Medinipur District. | Assistant Engineer | Junior Engiener,Junior Engineer | ORD/000538/2023-2024 | 1937/TD | 16/08/2023 | 28/03/2026 | MACKINTOSH BURN LIMITED | 10310.59 | 97.06 | 0.94 | 75
Total | [13 empty] | 10388.04 | 113.13 | 1.09