## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR | Contai-I | Tamluk Division | RAGHUSARDAR BAR JALPAI & IT'S ADJOINING MOUJAS PWSS | SM/13691 | New | Material Requisition To Resource Division |  |  | RTOR000170/2022-2023 | 2394/TD | 16/01/2023 | 16/01/2023 | Resource Division | 45.39 | 0 | 0 | 0
2 | PURBA MEDINIPUR | Contai-I | Midnapore Mechanical | RAGHUSARDAR BAR JALPAI & IT'S ADJOINING MOUJAS PWSS | SM/13691 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for RAGHUSARDAR BAR JALPAI and ADJOINING MOUJAS, Block Contai I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division | ORD/001666/2022-2023 | 549/W/MMD | 20/03/2023 | 01/03/2025 | DEBJYOTI BASU | 21.62 | 0 | 0 | 80
3 | PURBA MEDINIPUR | Contai-I | Tamluk Division | RAGHUSARDAR BAR JALPAI & IT'S ADJOINING MOUJAS PWSS | SM/13691 | New | Preparation of design based on soil test report and submission of drawing of foundation for construction of 150 cum RCC OHR at Raghusardarbar Jalpai PWSS at Contai-I Block under Tamluk Division,PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000882/2023-2024 | 204/TD | 10/01/2024 | 20/01/2024 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.96 | 0 | 0 | 100
4 | PURBA MEDINIPUR | Contai-I | Tamluk Division | RAGHUSARDAR BAR JALPAI & IT'S ADJOINING MOUJAS PWSS | SM/13691 | New | Material Requisition To Resource Division |  |  | RTOR000070/2024-2025 | 2976/TD | 12/09/2024 | 12/09/2024 | Resource Division | 5.96 | 0 | 0 | 0
5 | PURBA MEDINIPUR | Contai-I | Midnapore Mechanical | RAGHUSARDAR BAR JALPAI & IT'S ADJOINING MOUJAS PWSS | SM/13691 | New | Quotation for New service connection at TW-I of Raghu Sardarbar Jalpai ws scheme under MMD,PHE ,Dte. Ref Application no-2004579837, CON ID-204204431, under PICHABONI CCC, Block-Contai-I |  |  | BILL/03659/2023-2024 | BP-2023-24-662 | 12/02/2024 | 12/02/2024 | WBSEDCL | 4.25 | 0 | 0 | 0
Total | [13 empty] | 78.18 | 0 | 0