## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR | Contai-I | Midnapore Mechanical | KAPASDA & IT'S ADJOINING MOUJAS PWSS | SM/13692 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for KAPASDA and ADJOINING MOUJAS, Block ¿ contai I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division | ORD/001677/2022-2023 | 556/W/MMD | 20/03/2023 | 16/09/2023 | SHIVAM ENTERPRISE | 22.78 | 0 | 0 | 0
2 | PURBA MEDINIPUR | Contai-I | Tamluk Division | KAPASDA & IT'S ADJOINING MOUJAS PWSS | SM/13692 | New | Material Requisition To Resource Division |  |  | RTOR000313/2022-2023 | 2969/TD | 27/02/2023 | 27/02/2023 | Resource Division | 34.67 | 0 | 0 | 0
3 | PURBA MEDINIPUR | Contai-I | Tamluk Division | KAPASDA & IT'S ADJOINING MOUJAS PWSS | SM/13692 | New | Material Requisition To Resource Division |  |  | RTOR000093/2024-2025 | 2963/TD | 12/09/2024 | 12/09/2024 | Resource Division | 9.09 | 0 | 0 | 0
4 | PURBA MEDINIPUR | Contai-I | Tamluk Division | KAPASDA & IT'S ADJOINING MOUJAS PWSS | SM/13692 | New | Pump House ,200 cum OHR (Intze type with pile foundation), Rising main, Laying distribution pipe line, Boundary Wall, Soil investigation & Accommodate FHTC (845 nos) under JJM with allied work of KAPASDA PWSS within Contai-I Block under Contai Sub-Division of Tamluk Division, PHE Dte | Assistant Engineer | Junior Engineer | ORD/000279/2023-2024 | 554/TD | 12/05/2023 | 08/11/2023 | PATHIK PABAN NANDI | 453.18 | 0 | 0 | 50
5 | PURBA MEDINIPUR | Contai-I | Midnapore Mechanical | KAPASDA & IT'S ADJOINING MOUJAS PWSS | SM/13692 | New | Construction of materials godown alongwith internal electrification and illumination and other works at the campus of the office of Assistant Engineer under HESD, PHE Dte., Dist.- Purba Medinipur. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division | ORD/002725/2023-2024 | 1070/W/MMD | 14/03/2024 | 10/09/2024 | THE GODFATHER TRADING COMPANY | 10.42 | 0 | 0 | 100
Total | [13 empty] | 530.15 | 0 | 0