## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR | Potashpur-I | Midnapore Mechanical | CHANDPUR AND ADJOINING MOUJAS PWSS | SM/13693 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for CHANDPUR and ADJOINING MOUJAS, Block ¿ Potashpur I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001679/2022-2023 | 566/W/MMD | 20/03/2023 | 16/09/2023 | DEY ENTERPRISE | 22.8 | 0 | 0 | 0
2 | PURBA MEDINIPUR | Potashpur-I | Tamluk Division | CHANDPUR AND ADJOINING MOUJAS PWSS | SM/13693 | New | Sinking of Tube well,Pump House ,Construction of 200 cum OHR (Intze type with pile foundation), Rising main, Laying distribution pipe line, CC Pavement, Boundary Wall, Soil investigation & Accommodate FHTC (2655 nos) under JJM with allied work including 02(Two) Years Operation & Maintenance for Chandpur and Amarpur & its adjoining moujas PWSS within Patashpur-I Block within Contai Sub-Division under Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000679/2023-2024 | 2705/TD | 20/10/2023 | 30/05/2026 | TAPAS SANTRA | 939.05 | 136.67 | 14.55 | 70
3 | PURBA MEDINIPUR | Potashpur-I | Tamluk Division | CHANDPUR AND ADJOINING MOUJAS PWSS | SM/13693 | New | Material Requisition To Resource Division |  |  | RTOR000225/2022-2023 | 2704/TD | 06/02/2023 | 06/02/2023 | Resource Division | 22.02 | 0 | 0 | 0
4 | PURBA MEDINIPUR | Potashpur-I | Tamluk Division | CHANDPUR AND ADJOINING MOUJAS PWSS | SM/13693 | New | Material Requisition To Resource Division |  |  | RTOR000024/2024-2025 | 1639/TD | 18/06/2025 | 18/06/2025 | Resource Division | 8.37 | 0 | 0 | 0
5 | PURBA MEDINIPUR | Potashpur-I | Midnapore Mechanical | CHANDPUR AND ADJOINING MOUJAS PWSS | SM/13693 | New | Quotation Bill for New Service connection at T/W NO-I Of CHANDPUR W/S Scheme under MMD, PHE, Dte. Block- PATASHPUR-I, WBSEDCL SUPPLY OFFICE: AMARSHI C.C.C. Ref. Memo No- 2005076157/QUOT/03 DT. 05-02-2024 MEMO NO: AMR/PHE/686 DT. 05-02-2024 Application NO- 2005076157 Application type-New connection Consumer Id- 204520898 |  |  | BILL/04276/2024-2025 | C032554600635 | 17/03/2025 | 17/03/2025 | WBSEDCL | 5.23 | 0 | 0 | 0
6 | PURBA MEDINIPUR | Potashpur-I | Midnapore Mechanical | CHANDPUR AND ADJOINING MOUJAS PWSS | SM/13693 | New | Quotation Bill for New Service connection at T/W NO-II Of CHANDPUR W/S Scheme under MMD, PHE, Dte. Block- PATASHPUR-I, WBSEDCL SUPPLY OFFICE: AMARSHI C.C.C. Ref. Memo No- 2005076216/QUOT/03 DT. 05-02-2024 MEMO NO: AMR/PHE/687 DT. 05-02-2024 Application NO- 2005076216 Application type-New connection Consumer Id- 204520908 |  |  | BILL/04277/2024-2025 | C032554598872 | 17/03/2025 | 17/03/2025 | WBSEDCL | 3.7 | 0 | 0 | 0
Total | [13 empty] | 1001.16 | 136.67 | 13.65