## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR | Ramnagar-II | Tamluk Division | KALAPUNJA & IT'S ADJOINING MOUJAS PWSS | SM/13694 | New | Material Requisition To Resource Division |  |  | RTOR000263/2022-2023 | 2690/TD | 06/02/2023 | 06/02/2023 | Resource Division | 39.36 | 0 | 0 | 0
2 | PURBA MEDINIPUR | Ramnagar-II | Tamluk Division | KALAPUNJA & IT'S ADJOINING MOUJAS PWSS | SM/13694 | New | Material Requisition To Resource Division |  |  | RTOR000150/2023-2024 | 119/TD | 05/01/2024 | 05/01/2024 | Resource Division | 8.41 | 0 | 0 | 0
3 | PURBA MEDINIPUR | Ramnagar-II | Midnapore Mechanical | KALAPUNJA & IT'S ADJOINING MOUJAS PWSS | SM/13694 | New | Quotation Bill for New Service connection at T/W NO-I Of KALAPUNJA W/S Scheme under MMD, PHE, Dte. Block- RAMANAGR-II, WBSEDCL SUPPLY OFFICE: PICHABANI C.C.C. Ref. Memo No- 2004749309/QUOT/03 DT. 28-05-2024 Application NO- 2004749309 Application type-New connection Consumer Id- 204316972 |  |  | BILL/01146/2024-2025 | BP-2024-25-258 | 06/06/2024 | 06/06/2024 | WBSEDCL | 3.89 | 0 | 0 | 0
4 | PURBA MEDINIPUR | Ramnagar-II | Tamluk Division | KALAPUNJA & IT'S ADJOINING MOUJAS PWSS | SM/13694 | New | Payment to WBSEDCL for Shifting of 11KV HT maithana feeder for Kalapunja PWSS |  |  | BILL/01994/2023-2024 | BP-2023-24-938 | 06/03/2024 | 06/03/2024 | WBSEDCL | 2.16 | 0 | 0 | 0
5 | PURBA MEDINIPUR | Ramnagar-II | Midnapore Mechanical | KALAPUNJA & IT'S ADJOINING MOUJAS PWSS | SM/13694 | New | Quotation Bill for New Service connection at T/W NO-II Of KALAPUNJA W/S Scheme under MMD, PHE, Dte. Block- RAMNAGAR-II, WBSEDCL SUPPLY OFFICE: PICHABANI C.C.C. Ref. Memo No- 2004670828/QUOT/03 DT. 05-04-2024 Application NO- 2004670828 Application type-New connection Consumer Id- 204266383 |  |  | BILL/00301/2024-2025 | BP-2024-25-43 | 18/04/2024 | 18/04/2024 | WBSEDCL | 8.56 | 0 | 0 | 0
6 | PURBA MEDINIPUR | Ramnagar-II | Tamluk Division | KALAPUNJA & IT'S ADJOINING MOUJAS PWSS | SM/13694 | New | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House, Pipe carrying structure & Providing Functional Household Tap Connection (3154 Nos) For 2 nos Pipe water supply Scheme including two years Operation & Maintainance for DEPAL and KALAPUNJA within Ramnagar-II Block Under Digha Sub Division of Tamluk Division, PHE. Dept, Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000422/2023-2024 | 1416/TD | 12/07/2023 | 27/07/2025 | BASANTA KUMAR MAITY | 961.33 | 238.18 | 24.78 | 60
7 | PURBA MEDINIPUR | Ramnagar-II | Midnapore Mechanical | KALAPUNJA & IT'S ADJOINING MOUJAS PWSS | SM/13694 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for KALAPUNJA and ADJOINING MOUJAS, Block ¿ Ramnagar II, District - Purba Medinipurunder JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division | ORD/000150/2023-2024 | 1376/W/MMD | 30/05/2023 | 30/04/2025 | MENAKA ENTERPRISE | 23.67 | 17.84 | 75.37 | 100
Total | [13 empty] | 1047.37 | 256.02 | 24.44