## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR | Potashpur-I | Tamluk Division | AYMABAR BARYA AND IT'S ADJOINING MOUJAS PWSS | SM/13696 | New | Material Requisition To Resource Division |  |  | RTOR000272/2022-2023 | 2703/TD | 06/02/2023 | 06/02/2023 | Resource Division | 15.41 | 0 | 0 | 0
2 | PURBA MEDINIPUR | Potashpur-I | Midnapore Mechanical | AYMABAR BARYA AND IT'S ADJOINING MOUJAS PWSS | SM/13696 | New | Quotation Bill for New Service connection at T/W NO-II Of AYMABAR BARIA W/S Scheme under MMD, PHE, Dte. Block- PATASHPUR-I, WBSEDCL SUPPLY OFFICE: AMARSHI C.C.C. Ref. Memo No- 2004878127/QUOT/03 DT. 30-08-2024 MEMO NO: AMR/PHE/350 DT. 30/08/2024 Application NO- 2004878127 Application type-New connection Consumer Id- 204387570 |  |  | BILL/02448/2024-2025 | C102415716055 | 05/10/2024 | 05/10/2024 | WBSEDCL | 3.99 | 0 | 0 | 0
3 | PURBA MEDINIPUR | Potashpur-I | Midnapore Mechanical | AYMABAR BARYA AND IT'S ADJOINING MOUJAS PWSS | SM/13696 | New | Quotation Bill for New Service connection at T/W NO-I Of AYMABAR BERYA W/S Scheme under MMD, PHE, Dte. Block- PATASHPUR-I, WBSEDCL SUPPLY OFFICE: AMARSHI C.C.C. Ref. Memo No-2004775224/QUOT/03 DT. 14-06-2024 Application NO- 2004775224 Application type-New connection Consumer Id- 204330602 |  |  | BILL/01331/2024-2025 | BP-2024-25-355 | 01/07/2024 | 01/07/2024 | WBSEDCL | 10.56 | 0 | 0 | 0
4 | PURBA MEDINIPUR | Potashpur-I | Midnapore Mechanical | AYMABAR BARYA AND IT'S ADJOINING MOUJAS PWSS | SM/13696 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for AYMABAR BARYA and ADJOINING MOUJAS, Block ¿ Potashpur I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001649/2022-2023 | 542/W/MMD | 20/03/2023 | 31/12/2025 | SOUMEN ELECTRIC | 21.56 | 15.29 | 70.89 | 60
Total | [13 empty] | 51.52 | 15.29 | 29.67