## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR | Egra-I | Midnapore Mechanical | BARTTANA & IT'S ADJOINING MOUJAS PWSS | SM/13697 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for BARTTANA and ADJOINING MOUJAS, Block ¿ Egra I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division | ORD/001681/2022-2023 | 565/W/MMD | 20/03/2023 | 31/07/2025 | DEY ENTERPRISE | 22.8 | 0 | 0 | 55
2 | PURBA MEDINIPUR | Egra-I | Tamluk Division | BARTTANA & IT'S ADJOINING MOUJAS PWSS | SM/13697 | New | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House & Providing Functional Household Tap Connection (61964 Nos) For 38 nos Pipe water supply Scheme including two years Operation & Maintainance within Patashpur-I, Patashpur-II , Egra-I and Deshapran Block Under Tamluk Division PHE Dte. Under Purba Medinipur District. | Assistant Engineer,Assistant Engineer, Headquaters | Junior Engineer | ORD/000677/2023-2024 | 2702/TD | 20/10/2023 | 30/03/2026 | MACKINTOSH BURN LIMITED | 19507.71 | 132.02 | 0.68 | 51
3 | PURBA MEDINIPUR | Egra-I | Tamluk Division | BARTTANA & IT'S ADJOINING MOUJAS PWSS | SM/13697 | New | Material Requisition To Resource Division |  |  | RTOR000134/2022-2023 | 2418/TD | 16/01/2023 | 16/01/2023 | Resource Division | 43.87 | 0 | 0 | 0
4 | PURBA MEDINIPUR | Egra-I | Tamluk Division | BARTTANA & IT'S ADJOINING MOUJAS PWSS | SM/13697 | New | Preparation of design based on soil test report and submission of drawing of foundation for construction of 250 cum RCC OHR at Barttana PWSS at Egra-I Block under Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000162/2024-2025 | 2074/TD | 24/06/2024 | 04/07/2024 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.95 | 0.95 | 100 | 100
5 | PURBA MEDINIPUR | Egra-I | Tamluk Division | BARTTANA & IT'S ADJOINING MOUJAS PWSS | SM/13697 | New | Quotation Bill for New Service connection at T/W NO-II Of BARTANA W/S Scheme under MMD, PHE, Dte. Block- EGRA-I, WBSEDCL SUPPLY OFFICE: EGRA C.C.C. Ref. Memo No- 2004874714/QUOT/03/296 DT. 03-09-2024 Application NO- 2004874714 Application type-New connection Consumer Id- 204386343 |  |  | BILL/01002/2024-2025 | BP-2024-25-631 | 26/11/2024 | 26/11/2024 | WBSEDCL | 14.38 | 0 | 0 | 0
6 | PURBA MEDINIPUR | Egra-I | Midnapore Mechanical | BARTTANA & IT'S ADJOINING MOUJAS PWSS | SM/13697 | New | Quotation Bill for New Service connection at T/W NO-I Of BARTANA W/S Scheme under MMD, PHE, Dte. Block- EGRA-I, WBSEDCL SUPPLY OFFICE: EGRA C.C.C. Ref. Memo No- 2004660093/QUOT/03 DT. 01-04-2024 Application NO- 2004672007 Application type-New connection Consumer Id- 204261081 |  |  | BILL/00521/2024-2025 | BP-2024-25-96 | 24/04/2024 | 24/04/2024 | WBSEDCL | 5.33 | 0 | 0 | 0
7 | PURBA MEDINIPUR | Egra-I | Tamluk Division | BARTTANA & IT'S ADJOINING MOUJAS PWSS | SM/13697 | New | Material Requisition To Resource Division |  |  | RTOR000011/2025-2026 | 2072/TD | 12/08/2025 | 12/08/2025 | Resource Division | 10.1 | 0 | 0 | 0
Total | [13 empty] | 19605.13 | 132.97 | 0.68