## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR | Sutahata | Tamluk Division | URDDHABMAL AND ADJOINING MOUJAS PWSS | SM/13698 | New | Material Requisition To Resource Division |  |  | RTOR000160/2022-2023 | 2475/TD | 16/01/2023 | 16/01/2023 | Resource Division | 17 | 0 | 0 | 0
2 | PURBA MEDINIPUR | Sutahata | Midnapore Mechanical | URDDHABMAL AND ADJOINING MOUJAS PWSS | SM/13698 | New | Electric Quotation for URDHABMAL Water Supply Scheme T/W-I, (Ref. ID-204076039) |  |  | BILL/02197/2023-2024 | BP-2023-24-244 | 12/09/2023 | 12/09/2023 | WBSEDCL | 15.45 | 0 | 0 | 0
3 | PURBA MEDINIPUR | Sutahata | Midnapore Mechanical | URDDHABMAL AND ADJOINING MOUJAS PWSS | SM/13698 | New | Electric Quotation for URDHABMAL Water Supply Scheme T/W-II, (Ref. ID-204076027) |  |  | BILL/02199/2023-2024 | BP-2023-24-243 | 12/09/2023 | 12/09/2023 | WBSEDCL | 3.36 | 0 | 0 | 0
4 | PURBA MEDINIPUR | Sutahata | Tamluk Division | URDDHABMAL AND ADJOINING MOUJAS PWSS | SM/13698 | New | Ground water based Urddhabmal Water Supply Scheme by providing Construction of Pump House, Boundary Wall, Laying of Rising main, Laying of Distribution pipe line and FHTC (260 nos) work within Sutahata Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur.(Part-C) | Assistant Engineer | Junior Engineer | ORD/000784/2022-2023 | 3035/TD | 27/02/2023 | 28/04/2023 | R K CONSTRUCTION | 97.19 | 0 | 0 | 30
5 | PURBA MEDINIPUR | Sutahata | Tamluk Division | URDDHABMAL AND ADJOINING MOUJAS PWSS | SM/13698 | New | Ground water based Urddhabmal Water Supply Scheme by providing Laying of Distribution pipe line and FHTC (140 nos) work within Sutahata Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur.(Part-E) | Assistant Engineer | Junior Engineer | ORD/000785/2022-2023 | 3036/TD | 27/02/2023 | 29/03/2023 | CEM ENGINEERS CO-OPERATIVE SOCIETY LTD. | 39 | 0 | 0 | 65
6 | PURBA MEDINIPUR | Sutahata | Tamluk Division | URDDHABMAL AND ADJOINING MOUJAS PWSS | SM/13698 | New | Ground water based Urddhabmal Water Supply Scheme by providing Laying of Distribution pipe line and FHTC(137 nos) work within Sutahata Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur.(Part-H) | Assistant Engineer | Junior Engineer | ORD/000786/2022-2023 | 3037/TD | 27/02/2023 | 19/03/2023 | M/S BLUE BIRD | 15.92 | 0 | 0 | 0
7 | PURBA MEDINIPUR | Sutahata | Tamluk Division | URDDHABMAL AND ADJOINING MOUJAS PWSS | SM/13698 | New | Ground water based Urddhabmal Water Supply Scheme by providing Laying of Distribution pipe line and FHTC(50 nos) work within Sutahata Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur.(Part-I) | Assistant Engineer | Junior Engineer | ORD/000787/2022-2023 | 3038/TD | 27/02/2023 | 19/03/2023 | SAYAN MAITY | 20.13 | 0 | 0 | 87
8 | PURBA MEDINIPUR | Sutahata | Tamluk Division | URDDHABMAL AND ADJOINING MOUJAS PWSS | SM/13698 | New | Ground water based Urddhabmal Water Supply Scheme by providing Laying of Distribution pipe line work within Sutahata Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur.(Part-J) | Assistant Engineer | Junior Engineer | ORD/000788/2022-2023 | 3039/TD | 27/02/2023 | 19/03/2023 | M/S BLUE BIRD | 15.99 | 0 | 0 | 85
9 | PURBA MEDINIPUR | Sutahata | Tamluk Division | URDDHABMAL AND ADJOINING MOUJAS PWSS | SM/13698 | New | Ground water based Urddhabmal Water Supply Scheme by providing Laying of Distribution pipe line and FHTC (120nos) work within Sutahata Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur.(Part-K) | Assistant Engineer | Junior Engineer | ORD/000789/2022-2023 | 3040/TD | 27/02/2023 | 19/03/2023 | SUDIP MANNA | 15.47 | 0 | 0 | 65
10 | PURBA MEDINIPUR | Sutahata | Tamluk Division | URDDHABMAL AND ADJOINING MOUJAS PWSS | SM/13698 | New | Ground water based Urddhabmal Water Supply Scheme by providing Laying of Distribution pipe line and FHTC(130nos) work within Sutahata Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur.(Part-L) | Assistant Engineer | Junior Engineer | ORD/000790/2022-2023 | 3041/TD | 27/02/2023 | 19/03/2023 | SAYAN MAITY | 19.92 | 0 | 0 | 72
11 | PURBA MEDINIPUR | Sutahata | Tamluk Division | URDDHABMAL AND ADJOINING MOUJAS PWSS | SM/13698 | New | Ground water based Urddhabmal Water Supply Scheme by providing Laying of Distribution pipe line and FHTC(140 nos) work within Sutahata Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur.(Part-F) | Assistant Engineer | Junior Engineer | ORD/000913/2022-2023 | 3559/TD | 29/03/2023 | 20/12/2024 | S. B. ASSOCIATES | 57.43 | 0 | 0 | 85
12 | PURBA MEDINIPUR | Sutahata | Tamluk Division | URDDHABMAL AND ADJOINING MOUJAS PWSS | SM/13698 | New | Ground water based Urddhabmal Water Supply Scheme by providing Laying of Distribution pipe line and FHTC (140 nos) work within Sutahata Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur.(Part-D) | Assistant Engineer | Junior Engineer | ORD/000105/2023-2024 | 170/TD | 10/04/2023 | 10/05/2023 | SK MAIDUL ISLAM | 40.83 | 0 | 0 | 78
13 | PURBA MEDINIPUR | Sutahata | Tamluk Division | URDDHABMAL AND ADJOINING MOUJAS PWSS | SM/13698 | New | Ground water based Urddhabmal Water Supply Scheme by providing Laying of Distribution pipe line and FHTC (450 nos) work and Construction of R.C.C. Over Head Reservoir of capacity 250 cum and staging height 20.00 mtr. with allied work including Sub Soil Investigation within Sutahata Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur.(Part-B) | Assistant Engineer | Junior Engineer | ORD/000248/2023-2024 | 526/TD | 11/05/2023 | 07/11/2023 | BANDHAB ENGINEERS CO-OPERATIVE SOCIETY LTD. | 172.54 | 0 | 0 | 22
14 | PURBA MEDINIPUR | Sutahata | Tamluk Division | URDDHABMAL AND ADJOINING MOUJAS PWSS | SM/13698 | New | Ground water based Urddhabmal Water Supply Scheme by providing Laying of Distribution pipe line and FHTC (230nos) work within Sutahata Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur.(Part-G) | Assistant Engineer | Junior Engineer | ORD/000914/2022-2023 | 3560/TD | 29/03/2023 | 20/12/2024 | S. B. ASSOCIATES | 67.13 | 0 | 0 | 65
15 | PURBA MEDINIPUR | Sutahata | Tamluk Division | URDDHABMAL AND ADJOINING MOUJAS PWSS | SM/13698 | New | Material Requisition To Resource Division |  |  | RTOR000192/2023-2024 | 641/W | 20/02/2024 | 20/02/2024 | Resource Division | 11.07 | 0 | 0 | 0
16 | PURBA MEDINIPUR | Sutahata | Tamluk Division | URDDHABMAL AND ADJOINING MOUJAS PWSS | SM/13698 | New | Sinking of 2 (Two) nos. Tube Well at different sites. Name of Sites: i) Sinking of 250mm. x 150mm. dia. x 280 mtr. Deep additional Tube well by direct rotary rig method at 1st Tube well Site of Urddhabmal Water Supply Scheme within Sutahata Block under Haldia Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. ii) Sinking of 250mm. x 150mm. dia. x 280 mtr. Deep additional Tube well by direct rotary rig method at 2nd Tube well Site of Urddhabmal Water Supply Scheme within Sutahata Block under Haldia Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000894/2022-2023 | 3344/TD | 22/03/2023 | 16/04/2023 | M R ENTERPRISE | 30.86 | 0 | 0 | 50
17 | PURBA MEDINIPUR | Sutahata | Midnapore Mechanical | URDDHABMAL AND ADJOINING MOUJAS PWSS | SM/13698 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for URDDHABMAL and ADJOINING MOUJAS, Block ¿ Sutahata, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/001686/2022-2023 | 562/W/MMD | 20/03/2023 | 31/08/2025 | M/S B.M. ELECTRICAL | 22.81 | 0 | 0 | 70
18 | PURBA MEDINIPUR | Sutahata | Tamluk Division | URDDHABMAL AND ADJOINING MOUJAS PWSS | SM/13698 | New | Sinking of 250mm. x 150mm. dia. x 280 mtr. Deep additional Tube well by direct rotary rig method at 2nd Tube well Site of Urddhabmal Water Supply Scheme within Sutahata Block under Haldia Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. | Assistant Engineer |  | ORD/000145/2024-2025 | 2061/TD | 24/06/2024 | 14/07/2024 | KISHORE GHOSH | 14.87 | 0 | 0 | 0
19 | PURBA MEDINIPUR | Sutahata | Tamluk Division | URDDHABMAL AND ADJOINING MOUJAS PWSS | SM/13698 | New | Land Development work at Head work site & 2nd Tube well site of Urddhabmal Water supply Scheme within Sutahata Develompent Block under Haldia Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000381/2024-2025 | 1008/HSD, | 04/10/2024 | 12/05/2025 | TARUN KHATUA | 4.85 | 0 | 0 | 50
20 | PURBA MEDINIPUR | Sutahata | Tamluk Division | URDDHABMAL AND ADJOINING MOUJAS PWSS | SM/13698 | New | Ground water based Urddhabmal Water Supply Scheme by providing Construction of Pump House, Boundary Wall, Laying of Rising main, Laying of Distribution pipe line and FHTC (260 nos) work within Sutahata Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur.(Part-C) (Balance Part) | Assistant Engineer | Junior Engineer | ORD/000275/2024-2025 | 2902/TD | 10/09/2024 | 08/05/2025 | TARUN KHATUA | 68.16 | 0 | 0 | 50
Total | [13 empty] | 749.98 | 0 | 0