## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR | Bhagawanpur-I | Tamluk Division | PASCHIM BAR AND IT'S ADJOINING MOUJAS PWSS | SM/13699 | New | Sinking of Tube Well ,Construction of Pump House ,350 cum OHR (Intze type with pile foundation), Rising main, Laying distribution pipe line, Boundary Wall, Soil investigation & Accommodate FHTC (3181 nos) under JJM with allied work including 02 (two) Years Operation & Maintenance of PASCHIM BAR PWSS within Bhagwanpur-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer,Assistant Engineer, Headquaters | Junior Engineer | ORD/000220/2023-2024 | 447/TD | 04/05/2023 | 30/05/2026 | TAPAS SANTRA | 872.64 | 595.67 | 68.26 | 40
2 | PURBA MEDINIPUR | Bhagawanpur-I | Midnapore Mechanical | PASCHIM BAR AND IT'S ADJOINING MOUJAS PWSS | SM/13699 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for PASCHIM BAR and ADJOINING MOUJAS, Block ¿ Bhagwanpur I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001676/2022-2023 | 568/W/MMD | 20/03/2023 | 30/06/2024 | DEY ENTERPRISE | 25.26 | 23.59 | 93.38 | 75
3 | PURBA MEDINIPUR | Bhagawanpur-I | Tamluk Division | PASCHIM BAR AND IT'S ADJOINING MOUJAS PWSS | SM/13699 | New | Material Requisition To Resource Division |  |  | RTOR000246/2022-2023 | 2720/TD | 06/02/2023 | 06/02/2023 | Resource Division | 33.64 | 0 | 0 | 0
4 | PURBA MEDINIPUR | Bhagawanpur-I | Midnapore Mechanical | PASCHIM BAR AND IT'S ADJOINING MOUJAS PWSS | SM/13699 | New | Paschimbarh W/S scheme T/W No.-II (Laxmi Mandir) Applicatiot No.-2004522520 Ref.-204156806 |  |  | BILL/03179/2023-2024 | BP-2023-24-479 | 27/12/2023 | 27/12/2023 | WBSEDCL | 4.86 | 0 | 0 | 0
5 | PURBA MEDINIPUR | Bhagawanpur-I | Midnapore Mechanical | PASCHIM BAR AND IT'S ADJOINING MOUJAS PWSS | SM/13699 | New | Electric Quotation for PASCHIMBAR Water Supply Scheme T/W-I, (Ref. ID-204104644) |  |  | BILL/03057/2023-2024 | BP-2023-24-390 | 02/12/2023 | 02/12/2023 | WBSEDCL | 1.05 | 0 | 0 | 0
6 | PURBA MEDINIPUR | Bhagawanpur-I | Tamluk Division | PASCHIM BAR AND IT'S ADJOINING MOUJAS PWSS | SM/13699 | New | Laying Distribution System (Nodal-1-2,2-4,4-19,19-20,20-50,50-84,84-109,109-167 & 167-89) of pipe line and its allied works for PASCHIM BAR Water Supply Scheme in Bhgwanpur-I Block within Contai Sub-Division under Tamluk Division, PHE Dte, Purba Medinipur. | Assistant Engineer, Headquaters | Junior Engineer | ORD/001258/2023-2024 | 1072/TD | 16/03/2024 | 10/04/2024 | MISHRA ENTERPRISE | 23.45 | 21.38 | 91.17 | 80
7 | PURBA MEDINIPUR | Bhagawanpur-I | Tamluk Division | PASCHIM BAR AND IT'S ADJOINING MOUJAS PWSS | SM/13699 | New | Material Requisition To Resource Division |  |  | RTOR000163/2023-2024 | 128/TD | 05/01/2024 | 05/01/2024 | Resource Division | 19.59 | 0 | 0 | 0
8 | PURBA MEDINIPUR | Bhagawanpur-I | Midnapore Mechanical | PASCHIM BAR AND IT'S ADJOINING MOUJAS PWSS | SM/13699 | New | Hiring of Inspection Vehicle (Diesel/CNG/LPG Driven) for supervision and monitoring of different ongoing piped water supply scheme for covering Contai Sub Division and its adjacent Sub -Divisions under JJM Programe in the dist. of Purba Midnapore under MMD PHE Dte. w.e.f.-w.e.f 01-09-2025 to 31-08-2026. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division | ORD/000512/2025-2026 | 876/HESD | 29/08/2025 | 29/08/2026 | S.S.GHORAI | 4.78 | 0 | 0 | 0
9 | PURBA MEDINIPUR | Bhagawanpur-I | Tamluk Division | PASCHIM BAR AND IT'S ADJOINING MOUJAS PWSS | SM/13699 | New | Emergent repairing of Right Embankment of Kallaghal River in between ch 46.0 to 51.50 km within G.P.-Mahammadpur-I, Block-Bhagwanpur-I at Mouza- Uttarbar & Paschimber and P.S.-Bhagwanpur, Dist.-Purba Medinipur. |  |  | BILL/00007/2025-2026 |  | 04/04/2025 | 04/04/2025 | EXECUTIVE ENGINEER, CONTAI IRRIGATION DIVISION | 8.95 | 0 | 0 | 0
Total | [13 empty] | 994.21 | 640.63 | 64.44