## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Paniparul Zone-II | SM/13716 | Augmentation | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Paniparul Water Supply Scheme (Zone-II) under Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000320/2022-2023 | 590/TD | 17/06/2022 | 07/07/2022 | GEOTECHNICAL ENGINEERS CONSORTIUM | 3.77 | 3.77 | 100 | 100
2 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Paniparul Zone-II | SM/13716 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000232/2022-2023 | 2615/TD | 02/02/2023 | 02/02/2023 | Resource Division | 122.45 | 0 | 0 | 0
3 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Paniparul Zone-II | SM/13716 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000282/2022-2023 | 2635/TD | 02/02/2023 | 02/02/2023 | Resource Division | 23.91 | 0 | 0 | 0
4 | PURBA MEDINIPUR |  | Midnapore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Paniparul Zone-II | SM/13716 | Augmentation | Electric Quotation for PANIPARUL Water Supply Scheme T/W-II, Zone -II, (Ref. ID-204087320) |  |  | BILL/02896/2023-2024 | BP-2023-24-312 | 01/11/2023 | 01/11/2023 | WBSEDCL | 2.76 | 0 | 0 | 0
5 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Paniparul Zone-II | SM/13716 | Augmentation | Laying of distribution pipe line to accommodate FHTC with new construction of R.C.C. Elevated Reservoir of capacity 500cum and staging height 20.00 mtr. as per Departmental Drawing with allied works including supply of all labour & materials for Augmentation of Paniparul Zone-II Water Supply Scheme within Egra-II. Block under Digha sub-division of Tamluk Division, P.H.E.Dte, Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000723/2022-2023 | 2534/TD | 19/01/2023 | 01/07/2025 | BASANTA KUMAR MAITY | 644.68 | 352.62 | 54.7 | 78
6 | PURBA MEDINIPUR |  | Midnapore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Paniparul Zone-II | SM/13716 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Newly sunk Additional Tube well at PANIPARUL ZONE - II Water supply scheme, Egra -II block, District - Purba Medinipur under Midnapore Mechanical Division P.H.E. Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/002702/2023-2024 | 1051/W/MMD | 13/03/2024 | 02/04/2025 | GLACIER ENGINEERING CO. | 14 | 9.07 | 64.76 | 54
7 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Paniparul Zone-II | SM/13716 | Augmentation | Name of Work: Sinking of 3 (Three) nos. Tube Well at different sites. Name of Sites: i) Sinking of 300mm. x 200mm. dia. x 250 mtr. Deep Additional Tube well by direct rotary rig method at 2nd Tube well site of Paniparul Zone-II W/S Scheme within Egra-II Block under Digha Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. ii) Sinking of 300mm. x 200mm. dia. x 250 mtr. Deep Additional Tube well by direct rotary rig method at 3rd Tube well site of Paniparul Zone-II W/S Scheme within Egra-II Block under Digha Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. iii) Sinking of 300mm. x 200mm. dia. x 250 mtr. Deep Additional Tube well by direct rotary rig method at Head Work site Tube well of Paniparul Zone-II W/S Scheme within Egra-II Block under Digha Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000022/2023-2024 | 120/TD | 06/04/2023 | 16/05/2023 | KALPANA BUILDERS | 57.98 | 52.05 | 89.76 | 100
8 | PURBA MEDINIPUR |  | Midnapore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Paniparul Zone-II | SM/13716 | Augmentation | Electric Quotation for PANIPARUL Water Supply Scheme T/W-I, Zone- II, (Ref. ID-204128964) |  |  | BILL/03056/2023-2024 | BP-2023-24-389 | 02/12/2023 | 02/12/2023 | WBSEDCL | 4.9 | 0 | 0 | 0
9 | PURBA MEDINIPUR |  | Midnapore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Paniparul Zone-II | SM/13716 | Augmentation | Quotation Bill for New Service connection at T/W NO-III, ZONE-II Of PANIPARUL W/S Scheme under MMD, PHE, Dte. Block- EGRA-II, WBSEDCL SUPPLY OFFICE: CHORPALIA C.C.C. Ref. Memo No- 2004773750/QUOT/03/483 DT. 18-06-2024 Application NO- 2004773750 Application type-New connection Consumer Id- 204332477 |  |  | BILL/01327/2024-2025 | BP-2024-25-360 | 01/07/2024 | 01/07/2024 | WBSEDCL | 3.41 | 0 | 0 | 0
10 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Paniparul Zone-II | SM/13716 | Augmentation | Construction of Pump House, Boundary Wall, Laying Rising main pipe line & Land development under JJM with allied works for Paniparul (Z-II ) PWSS within Egra-II Block including supply of all labour & materials under Digha Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000599/2023-2024 | 2194/TD | 01/09/2023 | 31/10/2023 | BASANTA KUMAR MAITY | 55.17 | 0 | 0 | 75
11 | PURBA MEDINIPUR |  | Midnapore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Paniparul Zone-II | SM/13716 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Water Based Piped Water Supply Scheme for Paniparul Zone-II, Block ¿ Egra II, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001934/2022-2023 | 853/W/MMD | 24/03/2023 | 31/05/2025 | M/S S.G. ENTERPRISE | 26.86 | 24.84 | 92.49 | 80
Total | [13 empty] | 959.9 | 442.34 | 46.08