## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR | Contai-I | Tamluk Division | MUKUNDAPUR & IT'S ADJOINING MOUJAS PWSS | SM/13740 | New | Material Requisition To Resource Division |  |  | RTOR000165/2022-2023 | 2393/TD | 16/01/2023 | 16/01/2023 | Resource Division | 30.99 | 0 | 0 | 0
2 | PURBA MEDINIPUR | Contai-I | Midnapore Mechanical | MUKUNDAPUR & IT'S ADJOINING MOUJAS PWSS | SM/13740 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for MUKUNDAPUR and ADJOINING MOUJAS, Block ¿ Contai I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division | ORD/001672/2022-2023 | 554/W/MMD | 20/03/2023 | 01/03/2025 | DEBJYOTI BASU | 22.8 | 0 | 0 | 55
3 | PURBA MEDINIPUR | Contai-I | Tamluk Division | MUKUNDAPUR & IT'S ADJOINING MOUJAS PWSS | SM/13740 | New | Material Requisition To Resource Division |  |  | RTOR000085/2024-2025 | 2968/TD | 12/09/2024 | 12/09/2024 | Resource Division | 8.17 | 0 | 0 | 0
4 | PURBA MEDINIPUR | Contai-I | Midnapore Mechanical | MUKUNDAPUR & IT'S ADJOINING MOUJAS PWSS | SM/13740 | New | Quotation Bill for New Service connection at T/W NO-I Of MUKUNDAPUR W/S Scheme under MMD, PHE, Dte. Block- RAMANAGR-II, WBSEDCL SUPPLY OFFICE: PICHABANI C.C.C. Ref. Memo No- 2004749319/QUOT/03 DT. 28-05-2024 Application NO- 2004749319 Application type-New connection Consumer Id- 204315788 |  |  | BILL/01145/2024-2025 | BP-2024-25-259 | 06/06/2024 | 06/06/2024 | WBSEDCL | 2.83 | 0 | 0 | 0
5 | PURBA MEDINIPUR | Contai-I | Tamluk Division | MUKUNDAPUR & IT'S ADJOINING MOUJAS PWSS | SM/13740 | New | Bill for payment to WBSEDCL for Shifting of Electric Line for Mukundapur Water Supply Scheme under Tamluk Division, PHE Dte. |  |  | BILL/02049/2023-2024 | BP-2023-24-961 | 14/03/2024 | 14/03/2024 | WBSEDCL | 2.93 | 0 | 0 | 0
Total | [13 empty] | 67.73 | 0 | 0