## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR | Ramnagar-I | Midnapore Mechanical | NILKANTHAPUR & IT'S ADJOINING MOUJAS PWSS | SM/13741 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for NILKANTHAPUR and ADJOINING MOUJAS, Block ¿ Ramnagar I, District - Purba Medinipurunder JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000165/2023-2024 | 1407/W/MMD | 02/06/2023 | 15/08/2026 | SOUMEN ELECTRIC | 21.56 | 0 | 0 | 55
2 | PURBA MEDINIPUR | Ramnagar-I | Tamluk Division | NILKANTHAPUR & IT'S ADJOINING MOUJAS PWSS | SM/13741 | New | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House, Pipe carrying structure & Providing Functional Household Tap Connection (2813 Nos) For 2 nos Pipe Water Supply Scheme (Kainara & Nilkanthpur)including two years Operation & Maintainance work within Ramnagar-I Block Under Digha Sub Division of Tamluk Division, PHE. Dept, Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000681/2023-2024 | 2710/TD | 30/10/2023 | 28/12/2025 | TAPAS SANTRA | 866.03 | 144.34 | 16.67 | 85
3 | PURBA MEDINIPUR | Ramnagar-I | Tamluk Division | NILKANTHAPUR & IT'S ADJOINING MOUJAS PWSS | SM/13741 | New | Material Requisition To Resource Division |  |  | RTOR000277/2022-2023 | 2696/TD | 06/02/2023 | 06/02/2023 | Resource Division | 16.55 | 0 | 0 | 0
4 | PURBA MEDINIPUR | Ramnagar-I | Tamluk Division | NILKANTHAPUR & IT'S ADJOINING MOUJAS PWSS | SM/13741 | New | Material Requisition To Resource Division |  |  | RTOR000158/2023-2024 | 100/TD | 05/01/2024 | 05/01/2024 | Resource Division | 3.57 | 0 | 0 | 0
5 | PURBA MEDINIPUR | Ramnagar-I | Midnapore Mechanical | NILKANTHAPUR & IT'S ADJOINING MOUJAS PWSS | SM/13741 | New | Quotation for new service connection at TW-I of Nilkanthapur ws scheme under MMD,PHE Dte , Block-Ramnagar-I, DIGHA CCC Application no-2004764563 Con ID-204324292 |  |  | BILL/01233/2024-2025 | BP-2024-25-289 | 18/06/2024 | 18/06/2024 | WBSEDCL | 5.95 | 0 | 0 | 0
Total | [13 empty] | 913.67 | 144.34 | 15.8