## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR | Ramnagar-II | Tamluk Division | BHUIANJIBAR AND IT'S ADJOINING MOUJAS PWSS | SM/13742 | New | Material Requisition To Resource Division |  |  | RTOR000279/2022-2023 | 2688/TD | 06/02/2023 | 06/02/2023 | Resource Division | 24.43 | 0 | 0 | 0
2 | PURBA MEDINIPUR | Ramnagar-II | Tamluk Division | BHUIANJIBAR AND IT'S ADJOINING MOUJAS PWSS | SM/13742 | New | Material Requisition To Resource Division |  |  | RTOR000123/2023-2024 | 83/TD | 05/01/2024 | 05/01/2024 | Resource Division | 9.34 | 0 | 0 | 0
3 | PURBA MEDINIPUR | Ramnagar-II | Midnapore Mechanical | BHUIANJIBAR AND IT'S ADJOINING MOUJAS PWSS | SM/13742 | New | Quotation Bill for New Service connection at T/W NO-I Of BHUNIAJIBAR W/S Scheme under MMD, PHE, Dte. Block- RAMNAGAR-II, PICHABANI C.C.C. Ref. Memo No- 2004620665/QUOT/03 DT. 27-02-2024 Application NO- 2004620665 Application type-New connection Reference Id- 204229268 |  |  | BILL/04331/2023-2024 | BP-2023-24-807 | 11/03/2024 | 11/03/2024 | WBSEDCL | 3.18 | 0 | 0 | 0
4 | PURBA MEDINIPUR | Ramnagar-II | Midnapore Mechanical | BHUIANJIBAR AND IT'S ADJOINING MOUJAS PWSS | SM/13742 | New | Quotation Bill for New Service connection at T/W NO-II Of BHUIAJIBAR W/S Scheme under MMD, PHE, Dte. Block- RAMNAGAR-II, WBSEDCL SUPPLY OFFICE: PICHABANI C.C.C. Ref. Memo No- 2004950601/QUOT/03 DT. 30-10-2024 Application NO- 2004950601 Application type-New connection Consumer Id- 204434656 |  |  | BILL/03006/2024-2025 | C112423559210 | 20/11/2024 | 20/11/2024 | WBSEDCL | 3.4 | 0 | 0 | 0
5 | PURBA MEDINIPUR | Ramnagar-II | Midnapore Mechanical | BHUIANJIBAR AND IT'S ADJOINING MOUJAS PWSS | SM/13742 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for BHUIANJIBAR and ADJOINING MOUJAS, Block ¿ Ramnagar II, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division | ORD/001685/2022-2023 | 563/W/MMD | 20/03/2023 | 31/05/2025 | SUBHRA ENTERPRISE | 22.78 | 16.52 | 72.5 | 100
6 | PURBA MEDINIPUR | Ramnagar-II | Tamluk Division | BHUIANJIBAR AND IT'S ADJOINING MOUJAS PWSS | SM/13742 | New | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House, Pipe carrying structure & Providing Functional Household Tap Connection (3103 Nos) For 2 nos Pipe Water Supply Scheme including two years Operation & Maintainance for BHUINAJIBAR and DEULI within Ramnagar-II Block Under Digha Sub Division of Tamluk Division, PHE. Dept, Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000400/2023-2024 | 1068/TD | 08/06/2023 | 28/12/2025 | TAPAS SANTRA | 1110.29 | 444.54 | 40.04 | 85
Total | [13 empty] | 1173.44 | 461.06 | 39.29