## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR | Potashpur-II | Tamluk Division | KHAR & IT'S ADJOINING MOUJAS PWSS | SM/13743 | New | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House & Providing Functional Household Tap Connection (61964 Nos) For 38 nos Pipe water supply Scheme including two years Operation & Maintainance within Patashpur-I, Patashpur-II , Egra-I and Deshapran Block Under Tamluk Division PHE Dte. Under Purba Medinipur District. | Assistant Engineer,Assistant Engineer, Headquaters | Junior Engineer | ORD/000677/2023-2024 | 2702/TD | 20/10/2023 | 30/03/2026 | MACKINTOSH BURN LIMITED | 19507.71 | 22.13 | 0.11 | 51
2 | PURBA MEDINIPUR | Potashpur-II | Midnapore Mechanical | KHAR & IT'S ADJOINING MOUJAS PWSS | SM/13743 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for KHAR and ADJOINING MOUJAS, Block ¿ Potashpur II, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001674/2022-2023 | 569/W/MMD | 20/03/2023 | 31/07/2025 | DEY ENTERPRISE | 27.17 | 0 | 0 | 52
3 | PURBA MEDINIPUR | Potashpur-II | Tamluk Division | KHAR & IT'S ADJOINING MOUJAS PWSS | SM/13743 | New | Material Requisition To Resource Division |  |  | RTOR000153/2022-2023 | 2459/TD | 16/01/2023 | 16/01/2023 | Resource Division | 53.73 | 0 | 0 | 0
4 | PURBA MEDINIPUR | Potashpur-II | Tamluk Division | KHAR & IT'S ADJOINING MOUJAS PWSS | SM/13743 | New | Material Requisition To Resource Division |  |  | RTOR000048/2024-2025 | 1655/TD | 29/04/2024 | 29/04/2024 | Resource Division | 17.55 | 0 | 0 | 0
5 | PURBA MEDINIPUR | Potashpur-II | Midnapore Mechanical | KHAR & IT'S ADJOINING MOUJAS PWSS | SM/13743 | New | Quotation Bill for New Service connection at T/W NO-I Of KHAR W/S Scheme under MMD, PHE, Dte. Block- PATASHPUR-II, WBSEDCL SUPPLY OFFICE: PATSHPUR C.C.C. Ref. Memo No-2004886304/QUOT/03/581 DT. 06-09-2024 Application NO- 2004886304 Application type-New connection Consumer Id- 204391661 |  |  | BILL/02449/2024-2025 | C092443182184 | 27/09/2024 | 27/09/2024 | WBSEDCL | 3.56 | 0 | 0 | 0
6 | PURBA MEDINIPUR | Potashpur-II | Midnapore Mechanical | KHAR & IT'S ADJOINING MOUJAS PWSS | SM/13743 | New | Quotation Bill for New Service connection at T/W NO-II Of KHAR W/S Scheme under MMD, PHE, Dte. Block- POTASHPUR-II, WBSEDCL SUPPLY OFFICE: PATASPUR C.C.C. Ref. Memo No- 2004671992/QUOT/03/40 DT. 08-04-2024 Application NO- 2004671992 Application type-New connection Consumer Id- 204266827 |  |  | BILL/00501/2024-2025 | BP-2024-25-95 | 24/04/2024 | 24/04/2024 | WBSEDCL | 5.83 | 0 | 0 | 0
7 | PURBA MEDINIPUR | Potashpur-II | Tamluk Division | KHAR & IT'S ADJOINING MOUJAS PWSS | SM/13743 | New | Preparation of design based on soil test report and submission of drawing of foundation for construction of 450 cum RCC OHR at Khar at Patashpur - II Block under Tamluk Division, PHE Dte. | Assistant Engineer, Headquaters | Junior Engineer | ORD/000586/2024-2025 | 462/TD | 04/02/2025 | 14/02/2025 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.95 | 0 | 0 | 100
Total | [13 empty] | 19616.5 | 22.13 | 0.11