## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR | Ramnagar-II | Tamluk Division | DEULI & IT'S ADJOINING MOUJAS PWSS | SM/13744 | New | Material Requisition To Resource Division |  |  | RTOR000262/2022-2023 | 2689/TD | 06/02/2023 | 06/02/2023 | Resource Division | 43.3 | 0 | 0 | 0
2 | PURBA MEDINIPUR | Ramnagar-II | Tamluk Division | DEULI & IT'S ADJOINING MOUJAS PWSS | SM/13744 | New | Material Requisition To Resource Division |  |  | RTOR000130/2023-2024 | 84/TD | 05/01/2024 | 05/01/2024 | Resource Division | 9.77 | 0 | 0 | 0
3 | PURBA MEDINIPUR | Ramnagar-II | Midnapore Mechanical | DEULI & IT'S ADJOINING MOUJAS PWSS | SM/13744 | New | Quotation Bill for New Service connection at T/W NO-I Of DEULI W/S Scheme under MMD, PHE, Dte. Block- RAMNAGAR-II, PICHABANI C.C.C. Ref. Memo No- 2004641295/QUOT/03 DT. 12-03-2024 Application NO- 2004641295 Application type-New connection Consumer Id- 204244736 |  |  | BILL/04495/2023-2024 | BP-2023-24-863 | 16/03/2024 | 16/03/2024 | WBSEDCL | 3.7 | 0 | 0 | 0
4 | PURBA MEDINIPUR | Ramnagar-II | Midnapore Mechanical | DEULI & IT'S ADJOINING MOUJAS PWSS | SM/13744 | New | ADDITIONAL Quotation Bill for DEULI W/S SCHEME T/W NO- I , RAMNAGRA -II BLOCK . Ref. MEMO No- PBN/NS/36 Dt. 25.04.2024 Application NO- 100000106413 Dt. 25.04.2024 Reference Id- 860299003 REF CONSUMER ID: 204244736 WBSEDCL SUPPLY OFFICE: PICHABANI C.C.C. |  |  | BILL/00708/2024-2025 | BP-2024-25-147 | 09/05/2024 | 09/05/2024 | WBSEDCL | 0.84 | 0 | 0 | 0
5 | PURBA MEDINIPUR | Ramnagar-II | Midnapore Mechanical | DEULI & IT'S ADJOINING MOUJAS PWSS | SM/13744 | New | Quotation Bill for New Service connection at T/W NO-II Of DEULI W/S Scheme under MMD, PHE, Dte. Block- RAMANAGR-II, WBSEDCL SUPPLY OFFICE: PICHABANI C.C.C. Ref. Memo No- 2004670691/QUOT/03 DT. 05-04-2024 Application NO- 2004670691 Application type-New connection Consumer Id- 204266384 |  |  | BILL/00298/2024-2025 | BP-2024-25-44 | 18/04/2024 | 18/04/2024 | WBSEDCL | 3.7 | 0 | 0 | 0
6 | PURBA MEDINIPUR | Ramnagar-II | Tamluk Division | DEULI & IT'S ADJOINING MOUJAS PWSS | SM/13744 | New | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House, Pipe carrying structure & Providing Functional Household Tap Connection (3103 Nos) For 2 nos Pipe Water Supply Scheme including two years Operation & Maintainance for BHUINAJIBAR and DEULI within Ramnagar-II Block Under Digha Sub Division of Tamluk Division, PHE. Dept, Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000400/2023-2024 | 1068/TD | 08/06/2023 | 28/12/2025 | TAPAS SANTRA | 1110.29 | 405.43 | 36.52 | 85
7 | PURBA MEDINIPUR | Ramnagar-II | Midnapore Mechanical | DEULI & IT'S ADJOINING MOUJAS PWSS | SM/13744 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for DEULI and ADJOINING MOUJAS, Block ¿ Ramnagar II, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division | ORD/001683/2022-2023 | 564/W/MMD | 20/03/2023 | 15/04/2027 | DEY ENTERPRISE | 22.8 | 10.63 | 46.63 | 85
8 | PURBA MEDINIPUR | Ramnagar-II | Tamluk Division | DEULI & IT'S ADJOINING MOUJAS PWSS | SM/13744 | New | Canal crossing Structure for laying of Rising main line for Deuli & Its Adjoining Mouzas Water Supply Scheme within Ramnagar-II BLOCK under Digha Sub-Division of Tamluk Division , PHE Dte. ( Length of Rising main structure-1104.0m ) | Assistant Engineer | Junior Engineer | ORD/000302/2024-2025 | 2867/TD | 05/09/2024 | 05/10/2024 | TAPAS SANTRA | 38.23 | 0 | 0 | 100
Total | [13 empty] | 1232.63 | 416.07 | 33.75