## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR | Ramnagar-I | Tamluk Division | BISWANATHPUR PIPED WATER SUPPLY SCHEME. | SM/13850 | New | Sinking of Tube Well ,Construction of Pump House ,50 cum OHR (Intze type with pile foundation), Rising main, Laying distribution pipe line, Boundary Wall, Soil investigation & Accommodate FHTC (230 nos) under JJM with allied work including 02(Two) Years Operation & Maintenance of Biswanathpur PWSS within Ramnagar-I Block under Digha Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000181/2023-2024 | 292/TD | 20/04/2023 | 17/10/2023 | MAITY CONSTRUCTION | 170.3 | 91.4 | 53.67 | 55
2 | PURBA MEDINIPUR | Ramnagar-I | Midnapore Mechanical | BISWANATHPUR PIPED WATER SUPPLY SCHEME. | SM/13850 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for BISWANATHPUR PWSS, Block ¿ Ramnagar I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division | ORD/001728/2022-2023 | 600/W/MMD | 20/03/2023 | 31/07/2024 | M/S S M ELECTRICAL | 5.98 | 5.42 | 90.63 | 100
3 | PURBA MEDINIPUR | Ramnagar-I | Tamluk Division | BISWANATHPUR PIPED WATER SUPPLY SCHEME. | SM/13850 | New | Material Requisition To Resource Division |  |  | RTOR000268/2022-2023 | 2695/TD | 06/02/2023 | 06/02/2023 | Resource Division | 4.13 | 0 | 0 | 0
4 | PURBA MEDINIPUR | Ramnagar-I | Midnapore Mechanical | BISWANATHPUR PIPED WATER SUPPLY SCHEME. | SM/13850 | New | Biswanathpur W/S scheme TW-I Application no.-2004496775 Ref no.-204135775 |  |  | BILL/03194/2023-2024 | BP-2023-24-469 | 27/12/2023 | 27/12/2023 | WBSEDCL | 1.54 | 0 | 0 | 0
5 | PURBA MEDINIPUR | Ramnagar-I | Tamluk Division | BISWANATHPUR PIPED WATER SUPPLY SCHEME. | SM/13850 | New | Material Requisition To Resource Division |  |  | RTOR000124/2023-2024 | 106/TD | 05/01/2024 | 05/01/2024 | Resource Division | 1.42 | 0 | 0 | 0
6 | PURBA MEDINIPUR | Ramnagar-I | Midnapore Mechanical | BISWANATHPUR PIPED WATER SUPPLY SCHEME. | SM/13850 | New | Biswanathpur W/S scheme PH no.-II Application No.-2004521756 Ref.-204156072 |  |  | BILL/03244/2023-2024 | BP-2023-24-498 | 05/01/2024 | 05/01/2024 | WBSEDCL | 2.56 | 0 | 0 | 0
7 | PURBA MEDINIPUR | Ramnagar-I | Midnapore Mechanical | BISWANATHPUR PIPED WATER SUPPLY SCHEME. | SM/13850 | New | Hiring of Inspection Vehicle (Diesel/CNG/LPG Driven) for supervision and monitoring of different ongoing piped water supply scheme for covering Contai Sub Division and its adjacent Sub -Divisions under JJM Programe in the dist. of Purba Midnapore under MMD PHE Dte. w.e.f.-w.e.f 01-09-2025 to 31-08-2026. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division | ORD/000512/2025-2026 | 876/HESD | 29/08/2025 | 29/08/2026 | S.S.GHORAI | 4.78 | 0 | 0 | 0
Total | [13 empty] | 190.7 | 96.82 | 50.77