## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR | Mahisadal | Tamluk Division | BAKSHI CHAK SVS PIPED WATER SUPPLY SCHEME. | SM/13851 | New | Ground water based Bakshichak Water Supply Scheme by providing Sinking of Tube Well, Construction of Pump House, Boundary Wall, Laying of Rising main, Laying of Distribution pipe line and FHTC work within Mahishadal Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur.(Part-A) | Assistant Engineer | Junior Engineer | ORD/000149/2023-2024 | 276/TD | 20/04/2023 | 01/03/2026 | NARAYAN CHANDRA DAS | 84.8 | 52.91 | 62.4 | 39
2 | PURBA MEDINIPUR | Mahisadal | Tamluk Division | BAKSHI CHAK SVS PIPED WATER SUPPLY SCHEME. | SM/13851 | New | Ground water based Bakshichak Water Supply Scheme by Sub-Soil investigation, Construction of OHR - 50 Cum, within Mahishadal Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur.(Part-B) | Assistant Engineer | Junior Engineer | ORD/000384/2023-2024 | 1008/TD | 05/06/2023 | 21/11/2025 | ZENITH CONSTRUCTION | 45.79 | 0 | 0 | 5
3 | PURBA MEDINIPUR | Mahisadal | Central Drilling | BAKSHI CHAK SVS PIPED WATER SUPPLY SCHEME. | SM/13851 | New | Providing drilling crew and other allied works for construction of Tube Well ( 150mm X150mm X 270 Mtrs. Depth) by utilising Departmental Machineries for Bakshi Chak W/S Scheme (T/W-I) , Mahisadal Block under Purba Medinipur District, Central Drilling Division, P.H.E. Dte. | Driller In Charge | Junior Engineer | ORD/000119/2023-2024 | 1396/CDD | 19/09/2023 | 19/10/2023 | DEV AND COMPANY | 13.38 | 0 | 0 | 0
4 | PURBA MEDINIPUR | Mahisadal | Midnapore Mechanical | BAKSHI CHAK SVS PIPED WATER SUPPLY SCHEME. | SM/13851 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for BAKSHI CHAK, Block - Mahishadal, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/001671/2022-2023 | 571/W/MMD | 20/03/2023 | 31/08/2025 | DEY ENTERPRISE | 5.99 | 0 | 0 | 95
5 | PURBA MEDINIPUR | Mahisadal | Tamluk Division | BAKSHI CHAK SVS PIPED WATER SUPPLY SCHEME. | SM/13851 | New | Installation of display board at 4 (four) nos work site under Haldia Sub-Division of Tamluk Division, PHE Dte. (Phase-II) [Bakshichak PWSS, Bamanpur PWSS, Kanchanpur PWSS & Madhyahingli PWSS] | Assistant Engineer | Junior Engineer | ORD/000830/2023-2024 | 618/HSD | 21/12/2023 | 28/12/2023 | SNEHASIS BERA | 0.83 | 0.83 | 99.62 | 100
6 | PURBA MEDINIPUR | Mahisadal | Tamluk Division | BAKSHI CHAK SVS PIPED WATER SUPPLY SCHEME. | SM/13851 | New | Material Requisition To Resource Division |  |  | RTOR000328/2022-2023 | 2988/TD | 27/02/2023 | 27/02/2023 | Resource Division | 4.55 | 0 | 0 | 0
7 | PURBA MEDINIPUR | Mahisadal | Tamluk Division | BAKSHI CHAK SVS PIPED WATER SUPPLY SCHEME. | SM/13851 | New | Material Requisition To Resource Division |  |  | RTOR000116/2023-2024 | 80/TD | 05/01/2024 | 05/01/2024 | Resource Division | 1.53 | 0 | 0 | 0
8 | PURBA MEDINIPUR | Mahisadal | Tamluk Division | BAKSHI CHAK SVS PIPED WATER SUPPLY SCHEME. | SM/13851 | New | New Service connection at Baksichak w/s scheme PH I in the district of Purba Medinipur under MMD PHE Dte. (App No.- 2004980445, Ref ID 204456236) |  |  | BILL/01265/2024-2025 | BP-2024-25-648 | 17/01/2025 | 17/01/2025 | WBSEDCL | 12.43 | 0 | 0 | 0
Total | [13 empty] | 169.31 | 53.74 | 31.74