## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR | Mahisadal | Central Drilling | BAKSHI CHAK SVS PIPED WATER SUPPLY SCHEME. | SM/13851 | New | Providing drilling crew and other allied works for construction of Tube Well ( 150mm X150mm X 270 Mtrs. Depth) by utilising Departmental Machineries for Bakshi Chak W/S Scheme (T/W-I) , Mahisadal Block under Purba Medinipur District, Central Drilling Division, P.H.E. Dte. | Driller In Charge | Junior Engineer | ORD/000119/2023-2024 | 1396/CDD | 19/09/2023 | 19/10/2023 | DEV AND COMPANY | 13.38 | 0 | 0 | 0
2 | PURBA MEDINIPUR | Mahisadal | Tamluk Division | BAKSHI CHAK SVS PIPED WATER SUPPLY SCHEME. | SM/13851 | New | Material Requisition To Resource Division |  |  | RTOR000328/2022-2023 | 2988/TD | 27/02/2023 | 27/02/2023 | Resource Division | 4.55 | 0 | 0 | 0
3 | PURBA MEDINIPUR | Mahisadal | Tamluk Division | BAKSHI CHAK SVS PIPED WATER SUPPLY SCHEME. | SM/13851 | New | Installation of display board at 4 (four) nos work site under Haldia Sub-Division of Tamluk Division, PHE Dte. (Phase-II) [Bakshichak PWSS, Bamanpur PWSS, Kanchanpur PWSS & Madhyahingli PWSS] | Assistant Engineer | Junior Engineer | ORD/000830/2023-2024 | 618/HSD | 21/12/2023 | 28/12/2023 | SNEHASIS BERA | 0.83 | 0.83 | 99.62 | 100
4 | PURBA MEDINIPUR | Mahisadal | Tamluk Division | BAKSHI CHAK SVS PIPED WATER SUPPLY SCHEME. | SM/13851 | New | Material Requisition To Resource Division |  |  | RTOR000116/2023-2024 | 80/TD | 05/01/2024 | 05/01/2024 | Resource Division | 1.53 | 0 | 0 | 0
5 | PURBA MEDINIPUR | Mahisadal | Tamluk Division | BAKSHI CHAK SVS PIPED WATER SUPPLY SCHEME. | SM/13851 | New | Ground water based Bakshichak Water Supply Scheme by Sub-Soil investigation, Construction of OHR - 50 Cum, within Mahishadal Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur.(Part-B) | Assistant Engineer | Junior Engineer | ORD/000384/2023-2024 | 1008/TD | 05/06/2023 | 21/11/2025 | ZENITH CONSTRUCTION | 45.79 | 0 | 0 | 5
6 | PURBA MEDINIPUR | Mahisadal | Midnapore Mechanical | BAKSHI CHAK SVS PIPED WATER SUPPLY SCHEME. | SM/13851 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for BAKSHI CHAK, Block - Mahishadal, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/001671/2022-2023 | 571/W/MMD | 20/03/2023 | 31/08/2025 | DEY ENTERPRISE | 5.99 | 0 | 0 | 95
Total | [13 empty] | 72.08 | 0.83 | 1.15