## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR | Tamluk | Tamluk Division | AJANGECHHYA PIPED WATER SUPPLY SCHEME. | SM/13852 | New | Material Requisition To Resource Division |  |  | RTOR000224/2022-2023 | 2675/TD | 06/02/2023 | 06/02/2023 | Resource Division | 4.96 | 0 | 0 | 0
2 | PURBA MEDINIPUR | Tamluk | Midnapore Mechanical | AJANGECHHYA PIPED WATER SUPPLY SCHEME. | SM/13852 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for AJANGECHHYA, Block ¿ Tamluk, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/001661/2022-2023 | 545/W/MMD | 20/03/2023 | 09/03/2025 | DEBJYOTI BASU | 21.58 | 0 | 0 | 45
3 | PURBA MEDINIPUR | Tamluk | Midnapore Mechanical | AJANGECHHYA PIPED WATER SUPPLY SCHEME. | SM/13852 | New | AJANGECHIA w/s SCHEME Application No.-2004568912 Ref.-204196601 |  |  | BILL/03528/2023-2024 | BP-2023-24-586 | 02/02/2024 | 02/02/2024 | WBSEDCL | 5.6 | 0 | 0 | 0
4 | PURBA MEDINIPUR | Tamluk | Tamluk Division | AJANGECHHYA PIPED WATER SUPPLY SCHEME. | SM/13852 | New | Sinking of Tube Well, Construction of Pump House, 50 cum OHR (Intze type with pile foundation), Rising main, Laying distribution pipe line, Boundary Wall, Soil investigation & Accommodate FHTC (314 nos.), Installation of display Board, under JJM with allied work including 02 (two) Years Operation & Maintenance of Ajangechhya PWSS within Tamluk Block under Tamluk Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000077/2023-2024 | 208/TD | 13/04/2023 | 01/04/2025 | RELIABLE CONSTRUCTIONS | 135.23 | 0 | 0 | 45
Total | [13 empty] | 167.37 | 0 | 0