## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR | Contai-I | Midnapore Mechanical | PASCHIM RASULPUR AND IT'S ADJOINING MOUJAS | SM/13853 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for PASCHIM RASULPUR AND IT'S ADJOINING MOUJAS, Block ¿ Contai I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division | ORD/001711/2022-2023 | 594/W/MMD | 20/03/2023 | 16/09/2023 | INDIA ENTERPRISE | 21.62 | 0 | 0 | 0
2 | PURBA MEDINIPUR | Contai-I | Tamluk Division | PASCHIM RASULPUR AND IT'S ADJOINING MOUJAS | SM/13853 | New | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House & Providing Functional Household Tap Connection (32862 Nos), including 2 years Operation & Maintenance For 21 nos Pipe Water Supply Scheme within MOYNA AND CONTAI -I Block Under Tamluk Division PHE Dte. Under Purba Medinipur District. | Assistant Engineer | Junior Engiener,Junior Engineer | ORD/000538/2023-2024 | 1937/TD | 16/08/2023 | 28/03/2026 | MACKINTOSH BURN LIMITED | 10310.59 | 0 | 0 | 75
3 | PURBA MEDINIPUR | Contai-I | Tamluk Division | PASCHIM RASULPUR AND IT'S ADJOINING MOUJAS | SM/13853 | New | Material Requisition To Resource Division |  |  | RTOR000171/2022-2023 | 2395/TD | 16/01/2023 | 16/01/2023 | Resource Division | 25.23 | 0 | 0 | 0
4 | PURBA MEDINIPUR | Contai-I | Tamluk Division | PASCHIM RASULPUR AND IT'S ADJOINING MOUJAS | SM/13853 | New | Material Requisition To Resource Division |  |  | RTOR000082/2024-2025 | 2970/TD | 12/09/2024 | 12/09/2024 | Resource Division | 6.11 | 0 | 0 | 0
5 | PURBA MEDINIPUR | Contai-I | Midnapore Mechanical | PASCHIM RASULPUR AND IT'S ADJOINING MOUJAS | SM/13853 | New | Quotation Bill for New Service connection at T/W NO-I Of PASCHIM RASULPUR W/S Scheme under MMD, PHE, Dte. Block- CONTAI-I, WBSEDCL SUPPLY OFFICE: PICHABANI C.C.C. Ref. Memo No- 2005048465/QUOT/03 DT. 16-01-2025 Application NO- 2005048465 Application type-New connection Consumer Id- 204498741 |  |  | BILL/04504/2024-2025 | C032587408156 | 27/03/2025 | 27/03/2025 | WBSEDCL | 9.75 | 0 | 0 | 0
6 | PURBA MEDINIPUR | Contai-I | Midnapore Mechanical | PASCHIM RASULPUR AND IT'S ADJOINING MOUJAS | SM/13853 | New | Quotation Bill for New Service connection at T/W NO-II Of POTAPUKURIA W/S Scheme under MMD, PHE, Dte. Block- CONTAI-I, WBSEDCL SUPPLY OFFICE: PICHABANI C.C.C. Ref. Memo No- 2005367965/QUOT/03 DT. 31-07-2025 Application NO- 2005367965 Application type-New connection Consumer Id- 204682905 |  |  | BILL/01875/2025-2026 |  | 14/08/2025 | 14/08/2025 | WBSEDCL | 3.8 | 0 | 0 | 0
Total | [13 empty] | 10377.11 | 0 | 0