## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR | Contai-I | Tamluk Division | PASCHIM RASULPUR AND IT'S ADJOINING MOUJAS | SM/13853 | New | Material Requisition To Resource Division |  |  | RTOR000171/2022-2023 | 2395/TD | 16/01/2023 | 16/01/2023 | Resource Division | 25.23 | 0 | 0 | 0
2 | PURBA MEDINIPUR | Contai-I | Midnapore Mechanical | PASCHIM RASULPUR AND IT'S ADJOINING MOUJAS | SM/13853 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for PASCHIM RASULPUR AND IT'S ADJOINING MOUJAS, Block ¿ Contai I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division | ORD/001711/2022-2023 | 594/W/MMD | 20/03/2023 | 16/09/2023 | INDIA ENTERPRISE | 21.62 | 0 | 0 | 0
3 | PURBA MEDINIPUR | Contai-I | Tamluk Division | PASCHIM RASULPUR AND IT'S ADJOINING MOUJAS | SM/13853 | New | Material Requisition To Resource Division |  |  | RTOR000082/2024-2025 | 2970/TD | 12/09/2024 | 12/09/2024 | Resource Division | 6.11 | 0 | 0 | 0
Total | [13 empty] | 52.97 | 0 | 0