## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR | Contai-I | Tamluk Division | BAGURAN JALPAI AND IT'S ADJOINING MOUJAS | SM/13854 | New | Material Requisition To Resource Division |  |  | RTOR000173/2022-2023 | 2396/TD | 16/01/2023 | 16/01/2023 | Resource Division | 35.66 | 0 | 0 | 0
2 | PURBA MEDINIPUR | Contai-I | Midnapore Mechanical | BAGURAN JALPAI AND IT'S ADJOINING MOUJAS | SM/13854 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for BAGURAN JALPAI AND IT'S ADJOINING MOUJAS, Block ¿ Contai I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division | ORD/001721/2022-2023 | 596/W/MMD | 20/03/2023 | 01/03/2025 | T.S.CONSTRUCTION | 22.75 | 0 | 0 | 51
3 | PURBA MEDINIPUR | Contai-I | Tamluk Division | BAGURAN JALPAI AND IT'S ADJOINING MOUJAS | SM/13854 | New | Preparation of design based on soil test report and submission of drawing of foundation for construction of 200 cum RCC OHR at Baguran Jalpai PWSS at Contai-I Block under Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000230/2024-2025 | 2427/TD | 30/07/2024 | 09/08/2024 | ASTER CONSULTANCY | 0.95 | 0 | 0 | 100
4 | PURBA MEDINIPUR | Contai-I | Tamluk Division | BAGURAN JALPAI AND IT'S ADJOINING MOUJAS | SM/13854 | New | Material Requisition To Resource Division |  |  | RTOR000071/2024-2025 | 2948/TD | 12/09/2024 | 12/09/2024 | Resource Division | 8.06 | 0 | 0 | 0
5 | PURBA MEDINIPUR | Contai-I | Midnapore Mechanical | BAGURAN JALPAI AND IT'S ADJOINING MOUJAS | SM/13854 | New | Quotation Bill for New Service connection at T/W NO-I Of BAGURANJALPAI W/S Scheme under MMD, PHE, Dte. Block- CONTAI-I, WBSEDCL SUPPLY OFFICE: CONTAI C.C.C. Ref. Memo No- 2004689899/QUOT/03 DT. 19-04-2024 Application NO- 2004689899 Application type-New connection Consumer Id- 204279763 |  |  | BILL/00664/2024-2025 | BP-2024-25-111 | 06/05/2024 | 06/05/2024 | WBSEDCL | 3.63 | 0 | 0 | 0
6 | PURBA MEDINIPUR | Contai-I | Tamluk Division | BAGURAN JALPAI AND IT'S ADJOINING MOUJAS | SM/13854 | New | Shifting of 11kv HT Line (Junput feeder) at BAGURAN JALPAI WS SCHEME, BLOCK-Contai-1,CCC-CONTAI. Ref memono.-CD-322 Dated-14.05.2024 Ref. ID-860299651 Application ID-100000107869 |  |  | BILL/00421/2024-2025 | BP-2024-25-142 | 27/05/2024 | 27/05/2024 | WBSEDCL | 2.06 | 0 | 0 | 0
7 | PURBA MEDINIPUR | Contai-I | Tamluk Division | BAGURAN JALPAI AND IT'S ADJOINING MOUJAS | SM/13854 | New | Construction of Retaining wall for Protection of OHR site from Soil erosion and Land filling at Baguran Jalpai and its adjoing Mouzas- PWSS in Contai-I Block under Contai Sub-Division of Tamluk Division, P.H.E. Dte. Purba Medinipur. (For Low Land and existance of natural channel nearby) | Assistant Engineer | Junior Engineer | ORD/000387/2024-2025 | 3448/TD | 30/10/2024 | 18/05/2025 | BISWA NIRMAN ENTERPRISE. | 11.77 | 0 | 0 | 72
Total | [13 empty] | 84.87 | 0 | 0