## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR | Ramnagar-II | Tamluk Division | UTTAR GOPALPUR AND ADJOINING MOUJAS PWSS | SM/13855 | New | Laying distribution pipe line, & Accommodate FHTC (116 Nos) under JJM with allied work for Uttar Gopalpur & Its Adjoining Mouzas Water Supply Scheme within Ramnagar-II Block under Digha Sub-Division of Tamluk Division , PHED , Purba Medinipur (Part- E) | Assistant Engineer |  | ORD/000921/2022-2023 | 3558/TD | 29/03/2023 | 18/04/2023 | VENUS ENGINEERS CO-OPERATIVE SOCIETY LTD. | 14.49 | 8.15 | 56.25 | 60
2 | PURBA MEDINIPUR | Ramnagar-II | Tamluk Division | UTTAR GOPALPUR AND ADJOINING MOUJAS PWSS | SM/13855 | New | Material Requisition To Resource Division |  |  | RTOR000217/2022-2023 | 2687/TD | 06/02/2023 | 06/02/2023 | Resource Division | 21.28 | 0 | 0 | 0
3 | PURBA MEDINIPUR | Ramnagar-II | Tamluk Division | UTTAR GOPALPUR AND ADJOINING MOUJAS PWSS | SM/13855 | New | Laying distribution pipe line, & Accommodate FHTC (275 Nos) under JJM with allied work for Uttar Gopalpur & Its Adjoining Mouzas Water Supply Scheme within Ramnagar-II Block under Digha Sub-Division of Tamluk Division , PHED , Purba Medinipur (Part- D) | Assistant Engineer | Junior Engineer | ORD/000920/2022-2023 | 3557/TD | 29/03/2023 | 28/04/2023 | BUNBA CONSTRUCTION | 39.82 | 34.71 | 87.17 | 65
4 | PURBA MEDINIPUR | Ramnagar-II | Tamluk Division | UTTAR GOPALPUR AND ADJOINING MOUJAS PWSS | SM/13855 | New | Laying distribution pipe line, Pump House, Boundary Wall & Accommodate FHTC ( 695 Nos) under JJM with allied work for Uttar Gopalpur & Its Adjoining Mouzas Water Supply Scheme within Ramnagar-II Block under Digha Sub-Division of Tamluk Division , PHED , Purba Medinipur (Part - B ) | Assistant Engineer | Junior Engineer | ORD/000260/2023-2024 | 534/TD | 12/05/2023 | 18/06/2026 | M/S SREE DURGA ENTERPRISE | 199.79 | 154.02 | 77.09 | 75
5 | PURBA MEDINIPUR | Ramnagar-II | Tamluk Division | UTTAR GOPALPUR AND ADJOINING MOUJAS PWSS | SM/13855 | New | Laying distribution pipe line, & Accommodate FHTC ( 288 Nos) under JJM with allied work for Uttar Gopalpur & Its Adjoining Mouzas Water Supply Scheme within Ramnagar-II Block under Digha Sub-Division of Tamluk Division , PHED , Purba Medinipur (Part- C) | Assistant Engineer | Junior Engineer | ORD/000264/2023-2024 | 533/TD | 12/05/2023 | 20/05/2026 | M/S SREE DURGA ENTERPRISE | 111.4 | 91.22 | 81.89 | 82
6 | PURBA MEDINIPUR | Ramnagar-II | Central Drilling | UTTAR GOPALPUR AND ADJOINING MOUJAS PWSS | SM/13855 | New | Hiring of Diesel Driven Motor cab (BS-IV & Above) having contract carriage permit along with driver for the office of the Calcutta Mechanical Sub Division-ll (D),CDD, P.H.Enginering Dte. for supervision of JJM Related works. | Driller In Charge | Junior Engineer | ORD/000199/2023-2024 | 04/CMSD-II(D) | 11/01/2024 | 27/07/2024 | MD NIZAMUDDIN | 0.94 | 2.36 | 250.95 | 45
7 | PURBA MEDINIPUR | Ramnagar-II | Tamluk Division | UTTAR GOPALPUR AND ADJOINING MOUJAS PWSS | SM/13855 | New | Preparation of design based on soil test report and submission of drawing of foundation for construction of 300 cum RCC OHR at Uttar Gopalpur PWSS at Ramnagar-II Block under Tamluk Division,PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001047/2023-2024 | 377/TD | 29/01/2024 | 08/02/2024 | ASTER CONSULTANCY | 0.95 | 0.95 | 100 | 100
8 | PURBA MEDINIPUR | Ramnagar-II | Tamluk Division | UTTAR GOPALPUR AND ADJOINING MOUJAS PWSS | SM/13855 | New | Material Requisition To Resource Division |  |  | RTOR000173/2023-2024 | 109/TD | 05/01/2024 | 05/01/2024 | Resource Division | 11.75 | 0 | 0 | 0
9 | PURBA MEDINIPUR | Ramnagar-II | Midnapore Mechanical | UTTAR GOPALPUR AND ADJOINING MOUJAS PWSS | SM/13855 | New | Quotation for new service connection at TW-1 of Uttar Gopalpur ws scheme under MMD, PHE Dte. Ref. Application no-2004579816, Ref Con ID-204204428. PICHABONI CCC, Block-Ramnagar-II |  |  | BILL/03656/2023-2024 | BP-2023-24-677 | 15/02/2024 | 15/02/2024 | WBSEDCL | 4.27 | 0 | 0 | 0
10 | PURBA MEDINIPUR | Ramnagar-II | Midnapore Mechanical | UTTAR GOPALPUR AND ADJOINING MOUJAS PWSS | SM/13855 | New | Quotation for new service connection at TW-II of Uttar Gopalpur ws scheme under MMD,PHE Dte. Ref Application no-2004579836, CON ID-204204432, PICABONI CCC,Block-Ramnagar II |  |  | BILL/03653/2023-2024 | BP-2023-24-677 | 15/02/2024 | 15/02/2024 | WBSEDCL | 3.18 | 0 | 0 | 0
11 | PURBA MEDINIPUR | Ramnagar-II | Tamluk Division | UTTAR GOPALPUR AND ADJOINING MOUJAS PWSS | SM/13855 | New | Laying distribution pipe line, Pump House, Boundary Wall soil investigation, 300 Cum OHR ( with pile foundation ) & Accommodate FHTC ( 534 Nos) under JJM with allied work for Uttar Gopalpur & Its Adjoining Mouzas Water Supply Scheme within Ramnagar-II Block under Digha Sub-Division of Tamluk Division , PHED , Purba Medinipur (Part - A) | Assistant Engineer | Junior Engineer | ORD/000409/2023-2024 | 1095/TD | 08/06/2023 | 19/06/2026 | RELIABLE CONSTRUCTIONS | 253.87 | 107.87 | 42.49 | 25
12 | PURBA MEDINIPUR | Ramnagar-II | Tamluk Division | UTTAR GOPALPUR AND ADJOINING MOUJAS PWSS | SM/13855 | New | Drum Sheet walling , pipe line(for FHTC), road restoration, Accommodate FHTC (60 Nos) and others allied works under JJM for Uttar Gopalpur & Its Adjoining Mouzas Water Supply Scheme within Ramnagar-II Block under Digha Sub-Division of Tamluk Division , PHED , Purba Medinipur (Part ¿ A ) | Assistant Engineer |  | ORD/000534/2024-2025 | 210/TD | 15/01/2025 | 14/02/2025 | RELIABLE CONSTRUCTIONS | 23.37 | 0 | 0 | 0
13 | PURBA MEDINIPUR | Ramnagar-II | Central Drilling | UTTAR GOPALPUR AND ADJOINING MOUJAS PWSS | SM/13855 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 21/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 55.51 | 0.26 | 11
14 | PURBA MEDINIPUR | Ramnagar-II | Tamluk Division | UTTAR GOPALPUR AND ADJOINING MOUJAS PWSS | SM/13855 | New | Drum Sheet walling, left out pipe line, road restoration, Accommodate FHTC (27 Nos) and others allied works under JJM for Uttar Gopalpur & Its Adjoining Mouzas Water Supply Scheme within Ramnagar-II Block under Digha Sub-Division of Tamluk Division , PHED , Purba Medinipur (Part - B ) | Assistant Engineer | Junior Engineer | ORD/000298/2024-2025 | 3067/TD | 19/09/2024 | 19/10/2024 | DHANANJOY DAS | 34.51 | 0 | 0 | 2
Total | [13 empty] | 22059.4 | 454.79 | 2.06