## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR | Sutahata | Central Drilling | SIMULBERYA AND ITS ADJOINING MOUJAS PWSS | SM/13856 | New | Providing drilling crew and other allied works for construction of Tube Well ( 150mm X150mm X 270 Mtrs. Depth) by utilising Departmental Machineries for Simulberia W/S Scheme (T/W-I & II) , Sutahatal Block under Purba Medinipur District, Central Drilling Division, P.H.E. Dte. | Driller In Charge | Junior Engineer | ORD/000118/2023-2024 | 1397/CDD | 19/09/2023 | 19/10/2023 | MENAKA ENTERPRISE | 13.38 | 0 | 0 | 0
2 | PURBA MEDINIPUR | Sutahata | Tamluk Division | SIMULBERYA AND ITS ADJOINING MOUJAS PWSS | SM/13856 | New | Material Requisition To Resource Division |  |  | RTOR000302/2022-2023 | 3004/TD | 27/02/2023 | 27/02/2023 | Resource Division | 5.27 | 0 | 0 | 0
3 | PURBA MEDINIPUR | Sutahata | Tamluk Division | SIMULBERYA AND ITS ADJOINING MOUJAS PWSS | SM/13856 | New | Installation of 1 Nos. Display Board at Simulberya PWSS works sites under Haldia Sub-Division of Tamluk Division, PHE Dte. (Phase -VIII) | Assistant Engineer | Junior Engineer | ORD/001173/2023-2024 | 769/HSD, | 27/02/2024 | 05/03/2024 | SNEHASIS BERA | 0.21 | 0.21 | 99.62 | 100
4 | PURBA MEDINIPUR | Sutahata | Tamluk Division | SIMULBERYA AND ITS ADJOINING MOUJAS PWSS | SM/13856 | New | Material Requisition To Resource Division |  |  | RTOR000193/2023-2024 | 642/W | 20/02/2024 | 20/02/2024 | Resource Division | 2.94 | 0 | 0 | 0
5 | PURBA MEDINIPUR | Sutahata | Tamluk Division | SIMULBERYA AND ITS ADJOINING MOUJAS PWSS | SM/13856 | New | payment of Wayleave plan & survey charges SER-KGP-2024-WL-104 |  |  | BILL/00488/2024-2025 | BP-2024-25-190 | 14/06/2024 | 14/06/2024 | FA & CAO, S.E. RAILWAY, GRC. | 0.11 | 0 | 0 | 0
6 | PURBA MEDINIPUR | Sutahata | Midnapore Mechanical | SIMULBERYA AND ITS ADJOINING MOUJAS PWSS | SM/13856 | New | Quotation bill for new service connection at TW-I of Simulberia w/s scheme,Block-Sutahata,under MMD,PHE Dte. C.C.C-Chaitanyapur Application no.-2004695156 Application type-new connection Quotation Date-24/04/2024 Quotation Due Date-24/04/2025 Contract Demand-6000W |  |  | BILL/00648/2024-2025 | BP-2024-25-109 | 06/05/2024 | 06/05/2024 | WBSEDCL | 8.39 | 0 | 0 | 0
7 | PURBA MEDINIPUR | Sutahata | Tamluk Division | SIMULBERYA AND ITS ADJOINING MOUJAS PWSS | SM/13856 | New | Payment of Wayleave facility charges(Application ID-SER-KGP-2024-WL-104) |  |  | BILL/00693/2024-2025 | BP-2024-25-300 | 30/07/2024 | 30/07/2024 | FA & CAO, S.E. RAILWAY, GRC. | 6.21 | 0 | 0 | 0
8 | PURBA MEDINIPUR | Sutahata | Tamluk Division | SIMULBERYA AND ITS ADJOINING MOUJAS PWSS | SM/13856 | New | payment of Wayleave plan & survey charges SER-KGP-2024-WL-105 |  |  | BILL/00489/2024-2025 | BP-2024-25-191 | 14/06/2024 | 14/06/2024 | FA & CAO, S.E. RAILWAY, GRC. | 0.11 | 0 | 0 | 0
9 | PURBA MEDINIPUR | Sutahata | Tamluk Division | SIMULBERYA AND ITS ADJOINING MOUJAS PWSS | SM/13856 | New | Payment of Wayleave facility charges(Application ID-SER-KGP-2024-WL-105) |  |  | BILL/00692/2024-2025 | BP-2024-25-299 | 30/07/2024 | 30/07/2024 | FA & CAO, S.E. RAILWAY, GRC. | 6.27 | 0 | 0 | 0
10 | PURBA MEDINIPUR | Sutahata | Midnapore Mechanical | SIMULBERYA AND ITS ADJOINING MOUJAS PWSS | SM/13856 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for SIMULBERYA and ADJOINING MOUJAS, Block ¿ Sutahata, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/001670/2022-2023 | 553/W/MMD | 20/03/2023 | 01/02/2025 | DEBJYOTI BASU | 21.62 | 8.99 | 41.59 | 46
11 | PURBA MEDINIPUR | Sutahata | Tamluk Division | SIMULBERYA AND ITS ADJOINING MOUJAS PWSS | SM/13856 | New | Sinking of Tube Well, Construction of Pump House, Boundary Wall, Laying of Rising main, Sub-Soil investigation, Construction of OHR - 50 Cum, Laying of Distribution pipe line and FHTC work (477 nos) Including 2 years of Operation & Maintenance under JJM with alied work for ground water based Simulberya Water Supply Scheme within Sutahata Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000352/2023-2024 | 881/TD | 01/06/2023 | 01/12/2025 | BARH CONSTRUCTION | 177.2 | 44.07 | 24.87 | 30
Total | [13 empty] | 241.7 | 53.26 | 22.04