## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR | Potashpur-II | Tamluk Division | NONAKOURDA AND IT'S ADJOINING MOUJAS | SM/13857 | New | Material Requisition To Resource Division |  |  | RTOR000342/2022-2023 | 2997/TD | 27/02/2023 | 27/02/2023 | Resource Division | 8.93 | 0 | 0 | 0
2 | PURBA MEDINIPUR | Potashpur-II | Midnapore Mechanical | NONAKOURDA AND IT'S ADJOINING MOUJAS | SM/13857 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for NONAKOURDA and ADJOINING MOUJAS, Block ¿ Potashpur II, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001669/2022-2023 | 552/W/MMD | 20/03/2023 | 09/03/2025 | DEBJYOTI BASU | 21.62 | 0 | 0 | 55
3 | PURBA MEDINIPUR | Potashpur-II | Tamluk Division | NONAKOURDA AND IT'S ADJOINING MOUJAS | SM/13857 | New | Preparation of design based on soil test report and submission of drawing of foundation for construction of 150 cum RCC OHR at Nonakourda PWSS at Patashpur-II Block under Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000156/2024-2025 | 2068/TD | 24/06/2024 | 04/07/2024 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.95 | 0 | 0 | 100
4 | PURBA MEDINIPUR | Potashpur-II | Tamluk Division | NONAKOURDA AND IT'S ADJOINING MOUJAS | SM/13857 | New | Material Requisition To Resource Division |  |  | RTOR000034/2024-2025 | 1661/TD | 29/04/2024 | 29/04/2024 | Resource Division | 6.27 | 0 | 0 | 0
5 | PURBA MEDINIPUR | Potashpur-II | Midnapore Mechanical | NONAKOURDA AND IT'S ADJOINING MOUJAS | SM/13857 | New | Quotation Bill for New Service connection at T/W NO-II Of Nonakourda W/S Scheme under MMD, PHE, Dte. Block- POTASHPUR-II, WBSEDCL SUPPLY OFFICE: Patashpur ccc Ref. Memo No- 2004760157/QUOT/03 DT. 04-06-2024 Application NO- 2004760157 Application type-New connection Consumer Id- 204322028 |  |  | BILL/01238/2024-2025 | BP-2024-25-288 | 18/06/2024 | 18/06/2024 | WBSEDCL | 3.23 | 0 | 0 | 0
6 | PURBA MEDINIPUR | Potashpur-II | Tamluk Division | NONAKOURDA AND IT'S ADJOINING MOUJAS | SM/13857 | New | Tube well, Pump House ,150 cum OHR (Intze type with pile foundation), Rising main, Head work site, Laying distribution pipe line, Boundary Wall, Soil investigation & Accommodate FHTC (1018 nos) under JJM with allied work for Nonakourda- PWSS in Patashpur- II Block within Contai Sub-Division under Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000683/2023-2024 | 2684/TD | 16/10/2023 | 28/09/2025 | RELIABLE CONSTRUCTIONS | 352.4 | 0 | 0 | 30
Total | [13 empty] | 393.4 | 0 | 0