## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR | Moyna | Tamluk Division | GOURANGA CHAK AND ADJOINING MOUJAS PWSS | SM/13884 | New | Material Requisition To Resource Division |  |  | RTOR000169/2022-2023 | 2437/TD | 16/01/2023 | 16/01/2023 | Resource Division | 25.43 | 0 | 0 | 0
2 | PURBA MEDINIPUR | Moyna | Tamluk Division | GOURANGA CHAK AND ADJOINING MOUJAS PWSS | SM/13884 | New | Preparation of design based on soil test report and submission of drawing of foundation for construction of 200 cum RCC OHR at Gouranga Chak PWSS at Moyna block under Tamluk Division,PHE Dte. | Assistant Engineer | Junior Engiener | ORD/000873/2023-2024 | 195/TD | 10/01/2024 | 20/01/2024 | ASTER CONSULTANCY | 0.95 | 0.95 | 100 | 100
3 | PURBA MEDINIPUR | Moyna | Tamluk Division | GOURANGA CHAK AND ADJOINING MOUJAS PWSS | SM/13884 | New | Material Requisition To Resource Division |  |  | RTOR000008/2024-2025 | 1566/TD | 23/04/2024 | 23/04/2024 | Resource Division | 8.79 | 0 | 0 | 0
4 | PURBA MEDINIPUR | Moyna | Midnapore Mechanical | GOURANGA CHAK AND ADJOINING MOUJAS PWSS | SM/13884 | New | Quotation for new service connection at Gouranga chak w/s scheme PH II in the district of Purba Medinipur under MMD PHE Dte.( App No.- 2004709475, Ref ID 204293707) |  |  | BILL/01074/2024-2025 | BP-2024-25-189 | 24/05/2024 | 24/05/2024 | WBSEDCL | 4.34 | 0 | 0 | 0
5 | PURBA MEDINIPUR | Moyna | Midnapore Mechanical | GOURANGA CHAK AND ADJOINING MOUJAS PWSS | SM/13884 | New | Quotation for new service connection at Gouranga chak w/s scheme PH I in the district of Purba Medinipur under MMD PHE Dte.( App No.- 2004709436, Ref ID 204293706) |  |  | BILL/01075/2024-2025 | BP-2024-25-188 | 24/05/2024 | 24/05/2024 | WBSEDCL | 7.81 | 0 | 0 | 0
6 | PURBA MEDINIPUR | Moyna | Tamluk Division | GOURANGA CHAK AND ADJOINING MOUJAS PWSS | SM/13884 | New | Instalation of display Board at 5 nos { 1. CHONGRA PWSS( PUMP HOUSE -2) , 2. GOURANGA CHAK PWSS( PUMP HOUSE 1 & 2), 3.GHOJINA PWSS( PUMP HOUSE 1 & 2), all are under Moyna Development Block work site for Open Land under Tamluk Division, PHE Dte. Purba Medinipur District. | Assistant Engineer | Junior Engineer | ORD/000257/2025-2026 | 63/RWS/TSD | 06/05/2025 | 13/05/2025 | SUDIP MANNA | 0.83 | 0 | 0 | 100
Total | [13 empty] | 48.16 | 0.95 | 1.98