## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR | Moyna | Tamluk Division | GOURANGA CHAK AND ADJOINING MOUJAS PWSS | SM/13884 | New | Material Requisition To Resource Division |  |  | RTOR000169/2022-2023 | 2437/TD | 16/01/2023 | 16/01/2023 | Resource Division | 25.43 | 0 | 0 | 0
2 | PURBA MEDINIPUR | Moyna | Tamluk Division | GOURANGA CHAK AND ADJOINING MOUJAS PWSS | SM/13884 | New | Preparation of design based on soil test report and submission of drawing of foundation for construction of 200 cum RCC OHR at Gouranga Chak PWSS at Moyna block under Tamluk Division,PHE Dte. | Assistant Engineer | Junior Engiener | ORD/000873/2023-2024 | 195/TD | 10/01/2024 | 20/01/2024 | ASTER CONSULTANCY | 0.95 | 0.95 | 100 | 100
3 | PURBA MEDINIPUR | Moyna | Tamluk Division | GOURANGA CHAK AND ADJOINING MOUJAS PWSS | SM/13884 | New | Material Requisition To Resource Division |  |  | RTOR000008/2024-2025 | 1566/TD | 23/04/2024 | 23/04/2024 | Resource Division | 8.79 | 0 | 0 | 0
4 | PURBA MEDINIPUR | Moyna | Midnapore Mechanical | GOURANGA CHAK AND ADJOINING MOUJAS PWSS | SM/13884 | New | Quotation for new service connection at Gouranga chak w/s scheme PH II in the district of Purba Medinipur under MMD PHE Dte.( App No.- 2004709475, Ref ID 204293707) |  |  | BILL/01074/2024-2025 | BP-2024-25-189 | 24/05/2024 | 24/05/2024 | WBSEDCL | 4.34 | 0 | 0 | 0
5 | PURBA MEDINIPUR | Moyna | Midnapore Mechanical | GOURANGA CHAK AND ADJOINING MOUJAS PWSS | SM/13884 | New | Quotation for new service connection at Gouranga chak w/s scheme PH I in the district of Purba Medinipur under MMD PHE Dte.( App No.- 2004709436, Ref ID 204293706) |  |  | BILL/01075/2024-2025 | BP-2024-25-188 | 24/05/2024 | 24/05/2024 | WBSEDCL | 7.81 | 0 | 0 | 0
6 | PURBA MEDINIPUR | Moyna | Midnapore Mechanical | GOURANGA CHAK AND ADJOINING MOUJAS PWSS | SM/13884 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for GOURANGA CHAK and ADJOINING MOUJAS, Block ¿ Moyna, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/001682/2022-2023 | 558/W/MMD | 20/03/2023 | 26/02/2025 | DIPALI CONSTRUCTION | 22.63 | 20.32 | 89.78 | 80
7 | PURBA MEDINIPUR | Moyna | Tamluk Division | GOURANGA CHAK AND ADJOINING MOUJAS PWSS | SM/13884 | New | Preparation of design based on soil test report and submission of drawing of foundation for construction of 200 cum RCC OHR at Gouranga Chak PWSS at Moyna Block under Tamluk Division, PHE Dte. (Phase-II) | Assistant Engineer | Junior Engineer | ORD/000227/2024-2025 | 2428/TD | 30/07/2024 | 09/08/2024 | ASTER CONSULTANCY | 0.95 | 0.95 | 100 | 100
8 | PURBA MEDINIPUR | Moyna | Tamluk Division | GOURANGA CHAK AND ADJOINING MOUJAS PWSS | SM/13884 | New | Instalation of display Board at 5 nos { 1. CHONGRA PWSS( PUMP HOUSE -2) , 2. GOURANGA CHAK PWSS( PUMP HOUSE 1 & 2), 3.GHOJINA PWSS( PUMP HOUSE 1 & 2), all are under Moyna Development Block work site for Open Land under Tamluk Division, PHE Dte. Purba Medinipur District. | Assistant Engineer | Junior Engineer | ORD/000257/2025-2026 | 63/RWS/TSD | 06/05/2025 | 13/05/2025 | SUDIP MANNA | 0.83 | 0 | 0 | 100
9 | PURBA MEDINIPUR | Moyna | Tamluk Division | GOURANGA CHAK AND ADJOINING MOUJAS PWSS | SM/13884 | New | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House & Providing Functional Household Tap Connection (32862 Nos), including 2 years Operation & Maintenance For 21 nos Pipe Water Supply Scheme within MOYNA AND CONTAI -I Block Under Tamluk Division PHE Dte. Under Purba Medinipur District. | Assistant Engineer | Junior Engiener,Junior Engineer | ORD/000538/2023-2024 | 1937/TD | 16/08/2023 | 28/03/2026 | MACKINTOSH BURN LIMITED | 10310.59 | 245.75 | 2.38 | 75
10 | PURBA MEDINIPUR | Moyna | Midnapore Mechanical | GOURANGA CHAK AND ADJOINING MOUJAS PWSS | SM/13884 | New | Hiring of Inspection Vehicle (Diesel/CNG/LPG Driven) for supervision and monitoring of different ongoing piped water supply scheme for covering Tamluk Sub Division and its adjacent Sub -Divisions under JJM Programe for the office of Assistant Engineer, under Haldia Electrical Sub Division. P.H.E. Dte., under Purba Midnapore under MMD PHE Dte. w.e.f.-w.e.f 01-09-2025 to 31-08-2026. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000511/2025-2026 | 875/HESD | 29/08/2025 | 29/08/2026 | S.S.GHORAI | 4.78 | 0 | 0 | 40
Total | [13 empty] | 10387.12 | 267.98 | 2.58