## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR | Sahid Matangini | Tamluk Division | BARAGECHA AND ADJOINING MOUJAS PWSS | SM/13885 | New | Material Requisition To Resource Division |  |  | RTOR000209/2022-2023 | 2469/TD | 16/01/2023 | 16/01/2023 | Resource Division | 54.65 | 0 | 0 | 0
2 | PURBA MEDINIPUR | Sahid Matangini | Tamluk Division | BARAGECHA AND ADJOINING MOUJAS PWSS | SM/13885 | New | Material Requisition To Resource Division |  |  | RTOR000118/2023-2024 | 97//TD | 05/01/2024 | 05/01/2024 | Resource Division | 4.84 | 0 | 0 | 0
3 | PURBA MEDINIPUR | Sahid Matangini | Midnapore Mechanical | BARAGECHA AND ADJOINING MOUJAS PWSS | SM/13885 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for BARAGECHA and ADJOINING MOUJAS, Block ¿ Shahid Matangini, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/001664/2022-2023 | 547/W/MMD | 20/03/2023 | 01/09/2025 | DEBJYOTI BASU | 21.58 | 0 | 0 | 40
4 | PURBA MEDINIPUR | Sahid Matangini | Tamluk Division | BARAGECHA AND ADJOINING MOUJAS PWSS | SM/13885 | New | Sinking of Tube Well ,Construction of Pump House ,100 cum OHR (Intze type with pile foundation), Rising main, Laying distribution pipe line, Boundary Wall, Soil investigation & Accommodate FHTC (785 nos) under JJM with allied work including 02(two) Years Operation & Maintenance of BARAGECHA PWSS within Sahid Matangini Block under Tamluk Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000223/2023-2024 | 458/TD | 04/05/2023 | 20/10/2025 | TAPAS SANTRA | 308.25 | 0 | 0 | 50
Total | [13 empty] | 389.31 | 0 | 0