## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR | Contai-I | Tamluk Division | POTA PAKURIA AND IT'S ADJOINING MOUJAS | SM/13886 | New | Material Requisition To Resource Division |  |  | RTOR000175/2022-2023 | 2397/TD | 16/01/2023 | 16/01/2023 | Resource Division | 22.13 | 0 | 0 | 0
2 | PURBA MEDINIPUR | Contai-I | Midnapore Mechanical | POTA PAKURIA AND IT'S ADJOINING MOUJAS | SM/13886 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for POTA PAKURIA and ADJOINING MOUJAS, Block ¿ Contai I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division | ORD/001668/2022-2023 | 551/W/MMD | 20/03/2023 | 01/03/2025 | DEBJYOTI BASU | 21.62 | 0 | 0 | 80
3 | PURBA MEDINIPUR | Contai-I | Tamluk Division | POTA PAKURIA AND IT'S ADJOINING MOUJAS | SM/13886 | New | Preparation of design based on soil test report and submission of drawing of foundation for construction of 150 cum RCC OHR at Potapukuria PWSS at Contai-I Block under Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000176/2024-2025 | 2066/TD | 24/06/2024 | 04/07/2024 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.95 | 0 | 0 | 100
4 | PURBA MEDINIPUR | Contai-I | Tamluk Division | POTA PAKURIA AND IT'S ADJOINING MOUJAS | SM/13886 | New | Material Requisition To Resource Division |  |  | RTOR000078/2024-2025 | 2972/TD | 12/09/2024 | 12/09/2024 | Resource Division | 6.04 | 0 | 0 | 0
5 | PURBA MEDINIPUR | Contai-I | Midnapore Mechanical | POTA PAKURIA AND IT'S ADJOINING MOUJAS | SM/13886 | New | Quotation Bill for New Service connection at T/W NO-I Of POTA PUKURIA W/S Scheme under MMD, PHE, Dte. Block- RAMNAGAR-II, WBSEDCL SUPPLY OFFICE: PICHABANI C.C.C. Ref. Memo No- 2004670768/QUOT/03 DT. 05-04-2024 Application NO- 2004670768 Application type-New connection Consumer Id- 204266388 |  |  | BILL/00295/2024-2025 | BP-2024-25-45 | 18/04/2024 | 18/04/2024 | WBSEDCL | 3.45 | 0 | 0 | 0
Total | [13 empty] | 54.19 | 0 | 0