## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR | Ramnagar-II | Tamluk Division | BADALPUR AND IT'S ADJOINING MOUJAS | SM/13887 | New | Sinking of Tube Well ,Construction of Pump House ,100 cum OHR (Intze type with pile foundation), Rising main, Laying distribution pipe line, Boundary Wall, Soil investigation & Accommodate FHTC (635 nos) including 02(two) Years Operation & Maintenance under JJM with allied work of Badalpur PWSS within Ramnagar-II Block under Digha Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000351/2023-2024 | 853/TD | 31/05/2023 | 27/03/2026 | GHOSH CONSTRUCTION | 320.45 | 214.44 | 66.92 | 52
2 | PURBA MEDINIPUR | Ramnagar-II | Tamluk Division | BADALPUR AND IT'S ADJOINING MOUJAS | SM/13887 | New | Pump House ,Rising main, Laying distribution pipe line, Boundary Wall, & Accommodate FHTC (248nos) under JJM with allied work of BADALPUR PWSS within Contai-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000300/2023-2024 | 603/TD | 17/05/2023 | 13/10/2026 | AYSAN KHAN | 63.14 | 26.03 | 41.22 | 60
3 | PURBA MEDINIPUR | Ramnagar-II | Midnapore Mechanical | BADALPUR AND IT'S ADJOINING MOUJAS | SM/13887 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for BADALPUR and ADJOINING MOUJAS, Block ¿ Ramnagar II, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division | ORD/001662/2022-2023 | 546/W/MMD | 20/03/2023 | 09/03/2025 | DEBJYOTI BASU | 21.58 | 19.98 | 92.62 | 100
4 | PURBA MEDINIPUR | Ramnagar-II | Tamluk Division | BADALPUR AND IT'S ADJOINING MOUJAS | SM/13887 | New | Material Requisition To Resource Division |  |  | RTOR000260/2022-2023 | 2686/TD | 06/02/2023 | 06/02/2023 | Resource Division | 8.88 | 0 | 0 | 0
5 | PURBA MEDINIPUR | Ramnagar-II | Midnapore Mechanical | BADALPUR AND IT'S ADJOINING MOUJAS | SM/13887 | New | Electric Quotation for BADALPUR Water Supply Scheme T/W-I, (Ref. ID-204134593) |  |  | BILL/02999/2023-2024 | BP-2023-24-360 | 24/11/2023 | 24/11/2023 | WBSEDCL | 3.28 | 0 | 0 | 0
6 | PURBA MEDINIPUR | Ramnagar-II | Midnapore Mechanical | BADALPUR AND IT'S ADJOINING MOUJAS | SM/13887 | New | Badalpur W/S scheme PH-II Application no.-2004522472 ref.-204156771 |  |  | BILL/03196/2023-2024 | BP-2023-24-470 | 27/12/2023 | 27/12/2023 | WBSEDCL | 4.53 | 0 | 0 | 0
7 | PURBA MEDINIPUR | Ramnagar-II | Tamluk Division | BADALPUR AND IT'S ADJOINING MOUJAS | SM/13887 | New | Material Requisition To Resource Division |  |  | RTOR000114/2023-2024 | 78/TD | 05/01/2024 | 05/01/2024 | Resource Division | 3.91 | 0 | 0 | 0
Total | [13 empty] | 425.77 | 260.45 | 61.17