## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR | Sahid Matangini | Tamluk Division | GULURI AND IT'S ADJOING MOUJAS | SM/13888 | New | Material Requisition To Resource Division |  |  | RTOR000211/2022-2023 | 2470/TD | 16/01/2023 | 16/01/2023 | Resource Division | 25.32 | 0 | 0 | 0
2 | PURBA MEDINIPUR | Sahid Matangini | Tamluk Division | GULURI AND IT'S ADJOING MOUJAS | SM/13888 | New | Crossing permission of laying HDPE pipeline along and across of NH-116B of Guluri PWSS within Sahid Matangini Block under Tamluk Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer |  | ORD/001183/2023-2024 | 742/TD | 28/02/2024 | 19/03/2024 | DONA ASSOCIATES | 9.53 | 0 | 0 | 0
3 | PURBA MEDINIPUR | Sahid Matangini | Tamluk Division | GULURI AND IT'S ADJOING MOUJAS | SM/13888 | New | Land Development work at Headwork Site of Guluria Water Supply Scheme within Sahid Matangini Development Block under Tamluk Sadar Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000285/2024-2025 | 3050/TD | 19/09/2024 | 04/10/2024 | S.D. CONSTRUCTION | 5.82 | 0 | 0 | 100
4 | PURBA MEDINIPUR | Sahid Matangini | Tamluk Division | GULURI AND IT'S ADJOING MOUJAS | SM/13888 | New | Material Requisition To Resource Division |  |  | RTOR000138/2023-2024 | 131/TD | 05/01/2024 | 05/01/2024 | Resource Division | 8.48 | 0 | 0 | 0
5 | PURBA MEDINIPUR | Sahid Matangini | Midnapore Mechanical | GULURI AND IT'S ADJOING MOUJAS | SM/13888 | New | New electric Quotation as per bill for Guluri water supply scheme, T/W-II Matangini CCC Block- Sahid Matangini Application No.-2004770105 Consumer ID.-204328454 Date.-12/06/2024 |  |  | BILL/01283/2024-2025 | BP-2024-25-340 | 25/06/2024 | 25/06/2024 | WBSEDCL | 3.61 | 0 | 0 | 0
6 | PURBA MEDINIPUR | Sahid Matangini | Midnapore Mechanical | GULURI AND IT'S ADJOING MOUJAS | SM/13888 | New | Quotation Bill for New connection GULARI water supply scheme Head Work Site. Quotation Bill Date.-01/04/2024 Block-Kolaghat. Kolaghat CCC Application No.-2004662586 Ref no.-204260849 |  |  | BILL/00257/2024-2025 | BP-2024-25-28 | 15/04/2024 | 15/04/2024 | WBSEDCL | 4.85 | 0 | 0 | 0
7 | PURBA MEDINIPUR | Sahid Matangini | Midnapore Mechanical | GULURI AND IT'S ADJOING MOUJAS | SM/13888 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for GULURI and ADJOINING MOUJAS, Block ¿ Shahid Matangini, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/001680/2022-2023 | 557/W/MMD | 20/03/2023 | 09/03/2025 | SHIVAM ENTERPRISE | 22.78 | 0 | 0 | 75
8 | PURBA MEDINIPUR | Sahid Matangini | Tamluk Division | GULURI AND IT'S ADJOING MOUJAS | SM/13888 | New | Sinking of Tube Well ,Construction of Pump House ,200 cum OHR (Intze type with pile foundation), Rising main, Laying distribution pipe line, Boundary Wall, Soil investigation & Accommodate FHTC (1376 nos) under JJM with allied work including 02 (two) Years Operation & Maintenance of GULURI PWSS within Sahid Matangini Block under Tamluk Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000108/2023-2024 | 219/TD | 17/04/2023 | 03/10/2025 | TAPAS SANTRA | 384.71 | 0 | 0 | 60
Total | [13 empty] | 465.08 | 0 | 0