## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR | Bhagawanpur-II | Tamluk Division | ITA BARIA & ADJOINING MOUZAS | SM/14042 | New | Material Requisition To Resource Division |  |  | RTOR000310/2022-2023 | 2966/TD | 27/02/2023 | 27/02/2023 | Resource Division | 171.72 | 0 | 0 | 0
2 | PURBA MEDINIPUR | Bhagawanpur-II | Tamluk Division | ITA BARIA & ADJOINING MOUZAS | SM/14042 | New | Material Requisition To Resource Division |  |  | RTOR000182/2023-2024 | 631/W | 20/02/2024 | 20/02/2024 | Resource Division | 12.74 | 0 | 0 | 0
3 | PURBA MEDINIPUR | Bhagawanpur-II | Midnapore Mechanical | ITA BARIA & ADJOINING MOUZAS | SM/14042 | New | Quotation Bill for New Service connection at T/W NO-I Of ITABERIA W/S Scheme under MMD, PHE, Dte. Block- Bhagwanpur-II, MADHAKHALI C.C.C. Ref. Memo No- 2004601903/QUOT/03 DT. 15-02-2024 Application NO- 2004601903 Application type-New connection Reference Id- 204217836 |  |  | BILL/00599/2024-2025 |  | 24/04/2024 | 24/04/2024 | WBSEDCL | 3.54 | 0 | 0 | 0
4 | PURBA MEDINIPUR | Bhagawanpur-II | Midnapore Mechanical | ITA BARIA & ADJOINING MOUZAS | SM/14042 | New | Quotation Bill for Shifting of 33 KV FEEDER HT LINE AT SABITRAPUR( KANPUR W/S SCHEME ZONE-V, T/W NO-I) , RAMNAGRA -II BLOCK , DIGHA CCC, DIST.-PURBA MEDINIPUR. Ref. MEMO No- CD/1971 Dt. 22.02.2024 Application NO- 100000101137 Dt. 22/02/2024 Reference Id- 860292957 |  |  | BILL/04262/2023-2024 | BP-2023-24-813 | 13/03/2024 | 13/03/2024 | WBSEDCL | 3.05 | 0 | 0 | 0
5 | PURBA MEDINIPUR | Bhagawanpur-II | Midnapore Mechanical | ITA BARIA & ADJOINING MOUZAS | SM/14042 | New | Electric Quotation for ITABERIA Water Supply Scheme, T/W-I, (Ref. ID-204217836) |  |  | BILL/04345/2023-2024 | BP-2023-24-813 | 13/03/2024 | 13/03/2024 | WBSEDCL | 0.49 | 0 | 0 | 0
6 | PURBA MEDINIPUR | Bhagawanpur-II | Tamluk Division | ITA BARIA & ADJOINING MOUZAS | SM/14042 | New | Laying distribution pipe line & Accommodate FHTC (120 nos) under JJM with allied work for Ita Baria- PWSS in Bhagwanpur-II Block within Contai Sub-Division under Tamluk Division, PHE Dte. (PART-C) | Assistant Engineer | Junior Engineer | ORD/000906/2022-2023 | 3461/TD | 27/03/2023 | 09/03/2026 | JASODA ENTERPRISE | 62.76 | 0 | 0 | 85
7 | PURBA MEDINIPUR | Bhagawanpur-II | Tamluk Division | ITA BARIA & ADJOINING MOUZAS | SM/14042 | New | Laying distribution pipe line, Boundary Wall & Accommodate FHTC (320 nos) under JJM with allied work for Ita Baria- PWSS in Bhagwanpur-II Block within Contai Sub-Division under Tamluk Division, PHE Dte. (PART-E) | Assistant Engineer | Junior Engineer | ORD/000908/2022-2023 | 3463/TD | 27/03/2023 | 23/07/2025 | PARIA ENTERPRISE | 82.41 | 0 | 0 | 65
8 | PURBA MEDINIPUR | Bhagawanpur-II | Tamluk Division | ITA BARIA & ADJOINING MOUZAS | SM/14042 | New | Laying distribution pipe line & Accommodate FHTC (74 nos) under JJM with allied work for Ita Baria- PWSS in Bhagwanpur-II Block within Contai Sub-Division under Tamluk Division, PHE Dte. (PART-F) | Assistant Engineer | Junior Engineer | ORD/000909/2022-2023 | 3464/TD | 27/03/2023 | 20/01/2026 | LAKSHMI NARAYAN ENTERPRISE | 19.34 | 0 | 0 | 70
9 | PURBA MEDINIPUR | Bhagawanpur-II | Central Drilling | ITA BARIA & ADJOINING MOUZAS | SM/14042 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 21/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
10 | PURBA MEDINIPUR | Bhagawanpur-II | Tamluk Division | ITA BARIA & ADJOINING MOUZAS | SM/14042 | New | Laying distribution pipe line, & Accommodate FHTC (430 nos) under JJM with allied work for Ita Baria- PWSS in Bhagwanpur-II Block within Contai Sub-Division under Tamluk Division, PHE Dte. (PART-B) | Assistant Engineer | Junior Engineer | ORD/000282/2023-2024 | 565/TD | 12/05/2023 | 24/11/2025 | JASODA ENTERPRISE | 125.59 | 0 | 0 | 75
11 | PURBA MEDINIPUR | Bhagawanpur-II | Midnapore Mechanical | ITA BARIA & ADJOINING MOUZAS | SM/14042 | New | Construction of materials godown alongwith internal electrification and illumination and other works at the campus of the office of Assistant Engineer under HESD, PHE Dte., Dist.- Purba Medinipur. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division | ORD/002725/2023-2024 | 1070/W/MMD | 14/03/2024 | 10/09/2024 | THE GODFATHER TRADING COMPANY | 10.42 | 0 | 0 | 100
12 | PURBA MEDINIPUR | Bhagawanpur-II | Tamluk Division | ITA BARIA & ADJOINING MOUZAS | SM/14042 | New | 250 cum OHR (Intze type with pile foundation), Rising main, Laying distribution pipe line,Pump House , Boundary Wall, Soil investigation & Accommodate FHTC (460 nos) under JJM with allied work for Ita Baria- PWSS in Bhagwanpur Block within Contai Sub-Division under Tamluk Division, PHE Dte.(PART-A) | Assistant Engineer |  | ORD/000599/2024-2025 | 578/TD | 19/02/2025 | 18/08/2025 | ARABINDA GHOSH | 217.97 | 0 | 0 | 0
13 | PURBA MEDINIPUR | Bhagawanpur-II | Midnapore Mechanical | ITA BARIA & ADJOINING MOUZAS | SM/14042 | New | Supply and fitting fixing of porcelain fuse unit and aluminum armored cable for receiving service connection at different PWSS under Egra-II, Bhagwanpur-I and II Block under Medinapore Mechanical Division, P.H.E. Dte. in the dist. of Purba Medinipur. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000130/2024-2025 | 702/HESD | 19/07/2024 | 03/03/2025 | SOUMEN ELECTRIC | 2.2 | 0 | 0 | 70
Total | [13 empty] | 22051.99 | 0 | 0