## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Midnapore Mechanical | Augmentation of Ground Water Based Bar Sundara PWSS to Accommodate FHTC in Haldia Block under Haldia Sub-Division of Tamluk Division, in Purba Medinipur. | SM/14113 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Rejuvenation of Electro-Mechanical components of Barsundra PWSS in the District of Purba Medinipur under JJM programme, Block ¿ Haldia, District - Purba Medinipur under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/001545/2022-2023 | 396/W/MMD | 15/03/2023 | 11/09/2023 | BALAJI CONSTRUCTION | 12.4 | 11.59 | 93.47 | 60
2 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Bar Sundara PWSS to Accommodate FHTC in Haldia Block under Haldia Sub-Division of Tamluk Division, in Purba Medinipur. | SM/14113 | Augmentation | Land development of ditch and Approach Road with Box Culvert at 3rd T.W. site of Barsundra Water Supply Scheme under Haldia Sub-Division of Tamluk Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000104/2023-2024 | 214/TD | 17/04/2023 | 17/05/2023 | BISWANATH BHUNIA | 16.31 | 0 | 0 | 0
3 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Bar Sundara PWSS to Accommodate FHTC in Haldia Block under Haldia Sub-Division of Tamluk Division, in Purba Medinipur. | SM/14113 | Augmentation | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Barsundra Water Supply Scheme under Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000437/2021-2022 | 1518/TD | 07/01/2022 | 27/01/2022 | RADIANT | 4.5 | 4.5 | 100 | 100
4 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Bar Sundara PWSS to Accommodate FHTC in Haldia Block under Haldia Sub-Division of Tamluk Division, in Purba Medinipur. | SM/14113 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000231/2022-2023 | 2611/TD | 02/02/2023 | 02/02/2023 | Resource Division | 118.88 | 0 | 0 | 0
5 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Bar Sundara PWSS to Accommodate FHTC in Haldia Block under Haldia Sub-Division of Tamluk Division, in Purba Medinipur. | SM/14113 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000067/2023-2024 | 2643/TD | 13/10/2023 | 13/10/2023 | Resource Division | 36.47 | 0 | 0 | 0
6 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Bar Sundara PWSS to Accommodate FHTC in Haldia Block under Haldia Sub-Division of Tamluk Division, in Purba Medinipur. | SM/14113 | Augmentation | Augmentation of ground water based Barsundra Water Supply Scheme by providing Laying of Distribution to accommodate FHTC (5920 Nos),construction of R.C.C. Elevated Reservoir of capacity 750 cum and staging height 20.00 mtr. with allied works within Haldia Dev.Block under Haldia sub-division of Tamluk Division, P.H.E.Dte, Purba Medinipur | Assistant Engineer | Junior Engineer | ORD/000776/2022-2023 | 2860/TD | 17/02/2023 | 01/07/2025 | TAPAS SANTRA | 900.87 | 651.29 | 72.3 | 73
7 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Bar Sundara PWSS to Accommodate FHTC in Haldia Block under Haldia Sub-Division of Tamluk Division, in Purba Medinipur. | SM/14113 | Augmentation | Crossing permission of laying HDPE pipeline along and across of NH-116 of Barsundra Water Supply Scheme within Haldia Dev. Block under Haldia Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000823/2023-2024 | 3285/TD | 20/12/2023 | 09/01/2024 | DONA ASSOCIATES | 9.93 | 3.64 | 36.67 | 30
8 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Bar Sundara PWSS to Accommodate FHTC in Haldia Block under Haldia Sub-Division of Tamluk Division, in Purba Medinipur. | SM/14113 | Augmentation | Name of Work: Sinking of 4 (Four) nos. Tube Well at different sites. Name of Sites: i) Sinking of 300mm. x 200mm. dia. x 280 mtr. Deep Tube well by direct rotary rig method at 3rd Tube Tube well Site of Natshal Lakshya Zone-I Water Supply Scheme within Mahishadal Block under Haldia Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. ii) Sinking of 300mm. x 200mm. dia. x 280 mtr. Deep Tube well by direct rotary rig method at 3rd Tube Tube well Site of Natshal Lakshya Zone-II Water Supply Scheme within Mahishadal Block under Haldia Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. iii) Sinking of 300mm. x 200mm. dia. x 320 mtr. Deep Tube well by direct rotary rig method at 1st Tube Tube well Site of Barsundra Water Supply Scheme within Haldia Block under Haldia Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. iv) Sinking of 300mm. x 200mm. dia. x 320 mtr. Deep Tube well by direct rotary rig method at 3rd Tube Tube well Site of Barsundra Water Supply Scheme within Haldia Block under Haldia Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000334/2022-2023 | 1249/TD | 12/09/2022 | 22/10/2022 | SIMPLEX DRILLING COMPANY | 83.68 | 40.74 | 48.68 | 75
9 | PURBA MEDINIPUR |  | Midnapore Mechanical | Augmentation of Ground Water Based Bar Sundara PWSS to Accommodate FHTC in Haldia Block under Haldia Sub-Division of Tamluk Division, in Purba Medinipur. | SM/14113 | Augmentation | Additional works for providing and installation of submersible pumping machineries and other electromechanical equipments for Rejuvenation of elctro-mechanical components of Barsundra PWSS in the district of purba medinipur district under JJM program,Block-Haldia,under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/001560/2023-2024 | 951/HESD | 30/11/2023 | 07/12/2023 | BALAJI CONSTRUCTION | 0.69 | 0.54 | 77.98 | 100
10 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Bar Sundara PWSS to Accommodate FHTC in Haldia Block under Haldia Sub-Division of Tamluk Division, in Purba Medinipur. | SM/14113 | Augmentation | Installation of 4 Nos. Display Board at different PWSS works sites under Haldia Sub-Division of Tamluk Division, PHE Dte.(for Barsundra PWSS, Betkundu PWSS, Baramrit Beria PWSS, Amritberya PWSS) (Phase-VII) | Assistant Engineer | Junior Engineer | ORD/001172/2023-2024 | 768/HSD, | 27/02/2024 | 05/03/2024 | SNEHASIS BERA | 0.83 | 0.83 | 99.62 | 100
11 | PURBA MEDINIPUR |  | Midnapore Mechanical | Augmentation of Ground Water Based Bar Sundara PWSS to Accommodate FHTC in Haldia Block under Haldia Sub-Division of Tamluk Division, in Purba Medinipur. | SM/14113 | Augmentation | Quotation bill for shifting of PHE meter room with allied works at PH-I of Barsundra w/s scheme under MMD PHE Dte. Name of C.C.C.-Brajalalchak Reference ID-860311526 Application ID-100000117246 Quotation Date-27/08/2024 Quotation Due Date-25/11/2024 |  |  | BILL/02393/2024-2025 | C092404597616 | 05/09/2024 | 05/09/2024 | WBSEDCL | 1.38 | 0 | 0 | 0
12 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Bar Sundara PWSS to Accommodate FHTC in Haldia Block under Haldia Sub-Division of Tamluk Division, in Purba Medinipur. | SM/14113 | Augmentation | Laying of proposed Rising main line with inter connection ,Supply of DI Specials, at Head Work Site at Barsundara Water Supply Scheme within Haldia Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000234/2024-2025 | 2698/TD | 22/08/2024 | 16/09/2024 | ANIRBAN BHOWMIK | 10.21 | 0 | 0 | 0
13 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Bar Sundara PWSS to Accommodate FHTC in Haldia Block under Haldia Sub-Division of Tamluk Division, in Purba Medinipur. | SM/14113 | Augmentation | New Construction of boundary wall at 3rd T/W site (50mt) of Barsundra water supply scheme under Haldia Sub-Division PHE Dte.. | Assistant Engineer | Junior Engineer | ORD/000829/2022-2023 | 3168/TD | 10/03/2023 | 28/03/2025 | M/S SOURAV MAHAPATRA | 6.26 | 0 | 0 | 100
14 | PURBA MEDINIPUR |  | Midnapore Mechanical | Augmentation of Ground Water Based Bar Sundara PWSS to Accommodate FHTC in Haldia Block under Haldia Sub-Division of Tamluk Division, in Purba Medinipur. | SM/14113 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical Equipments for Augmentation of Ground Water Based BarSundara PWSS to Accommodate FHTC in Haldia Block under Haldia Sub-Division of Tamluk Division, in Purba Medinipur under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000124/2023-2024 | 1344/W/MMD | 24/05/2023 | 05/05/2025 | THE GODFATHER TRADING COMPANY | 26.94 | 20.24 | 75.15 | 60
Total | [13 empty] | 1229.34 | 733.36 | 59.65