## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR | Deshopran | Tamluk Division | BASANTIA AND IT'S ADJOINING MOUJAS PWSS | SM/14451 | New | Material Requisition To Resource Division |  |  | RTOR000314/2022-2023 | 2970/TD | 27/02/2023 |  | Resource Division | 21.24 | 0 | 0 | 0
2 | PURBA MEDINIPUR | Deshopran | Midnapore Mechanical | BASANTIA AND IT'S ADJOINING MOUJAS PWSS | SM/14451 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for BASANTIA AND IT'S ADJOINING MOUJAS, Block ¿ Deshopran, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division | ORD/001725/2022-2023 | 597/W/MMD | 20/03/2023 | 16/09/2023 | M/S. JIT ENTERPRISE | 22.8 | 0 | 0 | 0
3 | PURBA MEDINIPUR | Deshopran | Tamluk Division | BASANTIA AND IT'S ADJOINING MOUJAS PWSS | SM/14451 | New | Sinking of Tube well, Pump House, 300 cum OHR (Intze type with pile foundation), Rising main, Head work site, Laying distribution pipe line, Soil investigation & Accommodate FHTC (1581 nos) under JJM with allied work including 02(Two) Years Operation & Maintenance for Basantia and Adjoining Moujas PWSS in Deshapran Block within Contai Sub-Division under Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000421/2023-2024 | 1412/TD | 12/07/2023 | 08/01/2024 | JAYANTA KUMAR MONDAL | 413.14 | 24.51 | 5.93 | 85
Total | [13 empty] | 457.19 | 24.51 | 5.36