## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR | Deshopran | Midnapore Mechanical | BASANTIA AND IT'S ADJOINING MOUJAS PWSS | SM/14451 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for BASANTIA AND IT'S ADJOINING MOUJAS, Block ¿ Deshopran, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division | ORD/001725/2022-2023 | 597/W/MMD | 20/03/2023 | 16/09/2023 | M/S. JIT ENTERPRISE | 22.8 | 0 | 0 | 0
2 | PURBA MEDINIPUR | Deshopran | Tamluk Division | BASANTIA AND IT'S ADJOINING MOUJAS PWSS | SM/14451 | New | Sinking of Tube well, Pump House, 300 cum OHR (Intze type with pile foundation), Rising main, Head work site, Laying distribution pipe line, Soil investigation & Accommodate FHTC (1581 nos) under JJM with allied work including 02(Two) Years Operation & Maintenance for Basantia and Adjoining Moujas PWSS in Deshapran Block within Contai Sub-Division under Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000421/2023-2024 | 1412/TD | 12/07/2023 | 21/11/2026 | JAYANTA KUMAR MONDAL | 413.14 | 102.11 | 24.72 | 85
3 | PURBA MEDINIPUR | Deshopran | Tamluk Division | BASANTIA AND IT'S ADJOINING MOUJAS PWSS | SM/14451 | New | Material Requisition To Resource Division |  |  | RTOR000314/2022-2023 | 2970/TD | 27/02/2023 | 27/02/2023 | Resource Division | 21.24 | 0 | 0 | 0
4 | PURBA MEDINIPUR | Deshopran | Tamluk Division | BASANTIA AND IT'S ADJOINING MOUJAS PWSS | SM/14451 | New | Material Requisition To Resource Division |  |  | RTOR000074/2024-2025 | 2949/TD | 12/09/2024 | 12/09/2024 | Resource Division | 9.74 | 0 | 0 | 0
5 | PURBA MEDINIPUR | Deshopran | Midnapore Mechanical | BASANTIA AND IT'S ADJOINING MOUJAS PWSS | SM/14451 | New | Quotation Bill for New Service connection at T/W NO-I Of BASANTIA W/S Scheme under MMD, PHE, Dte. Block- CONTAI-II, WBSEDCL SUPPLY OFFICE: MUKUNDAPUR C.C.C. Ref. Memo No- 2004877659/QUOT/03 DT. 12-09-2024 Application NO- 2004877659 Application type-New connection Consumer Id- 204397982 |  |  | BILL/02496/2024-2025 | C092445108283 | 30/09/2024 | 30/09/2024 | WBSEDCL | 7.85 | 0 | 0 | 0
Total | [13 empty] | 474.78 | 102.11 | 21.51