## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR | Egra-II | Tamluk Division | BAINCHA AND IT'S ADJOINING MOUJAS PWSS | SM/14455 | New | Material Requisition To Resource Division |  |  | RTOR000255/2022-2023 | 2712/TD | 06/02/2023 | 06/02/2023 | Resource Division | 32.92 | 0 | 0 | 0
2 | PURBA MEDINIPUR | Egra-II | Midnapore Mechanical | BAINCHA AND IT'S ADJOINING MOUJAS PWSS | SM/14455 | New | Quotation Bill for New Service connection at T/W NO-I Of BAINCHA W/S Scheme under MMD, PHE, Dte. Block- Egra-II, BALIGHAI C.C.C. Ref. Memo No- 2004626460/QUOT/03 DT. 01-03-2024 Application NO- 2004626460 Application type-New connection Consumer Id- 204233927 |  |  | BILL/04507/2023-2024 | BP-2023-24-864 | 16/03/2024 | 16/03/2024 | WBSEDCL | 5.54 | 0 | 0 | 0
3 | PURBA MEDINIPUR | Egra-II | Midnapore Mechanical | BAINCHA AND IT'S ADJOINING MOUJAS PWSS | SM/14455 | New | "Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for BAINCHA AND ITS ADJOINING MOUJAS, Block ¿ Egra II, District - Purba Medinipur under JJM Program under MMD PHE Dte. ¿" | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/002040/2022-2023 | 948/W/MMD | 28/03/2023 | 31/08/2025 | A.S.ENTERPRISE | 21.57 | 9.57 | 44.38 | 90
4 | PURBA MEDINIPUR | Egra-II | Tamluk Division | BAINCHA AND IT'S ADJOINING MOUJAS PWSS | SM/14455 | New | Sinking of Tube Well ,Construction of Pump House ,150 cum OHR (Intze type with pile foundation), Rising main, Laying distribution pipe line, Boundary Wall, Soil investigation & Accommodate FHTC (880nos) under JJM with allied work including 02(two) Years Operation & Maintenance of Baincha PWSS within Egra-II Block under Digha Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000481/2023-2024 | 1566/TD | 19/07/2023 | 27/06/2025 | M/S JOY | 322.5 | 136.69 | 42.39 | 45
5 | PURBA MEDINIPUR | Egra-II | Tamluk Division | BAINCHA AND IT'S ADJOINING MOUJAS PWSS | SM/14455 | New | Land Development at HeadWorks site of Baincha Water Supply Scheme within Egra - II Block under Digha Sub-Division of Tamluk Division, P.H.E.Dte. Purba Medinipur. | Assistant Engineer |  | ORD/000208/2025-2026 | 1575/TD | 13/06/2025 | 20/06/2025 | M/S JOY | 4.75 | 0 | 0 | 0
Total | [13 empty] | 387.29 | 146.27 | 37.77