## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR | Ramnagar-I | Tamluk Division | GHANTA SHALA AND IT'S ADJOINING MOUJAS PWSS | SM/14456 | New | Material Requisition To Resource Division |  |  | RTOR000266/2022-2023 | 2694/TD | 06/02/2023 | 06/02/2023 | Resource Division | 26.6 | 0 | 0 | 0
2 | PURBA MEDINIPUR | Ramnagar-I | Tamluk Division | GHANTA SHALA AND IT'S ADJOINING MOUJAS PWSS | SM/14456 | New | Material Requisition To Resource Division |  |  | RTOR000135/2023-2024 | 105/TD | 05/01/2024 | 05/01/2024 | Resource Division | 4.14 | 0 | 0 | 0
3 | PURBA MEDINIPUR | Ramnagar-I | Midnapore Mechanical | GHANTA SHALA AND IT'S ADJOINING MOUJAS PWSS | SM/14456 | New | Electric Quotation for GHATASHALA Water Supply Scheme T/W-I, (Ref. ID-204135822) |  |  | BILL/03002/2023-2024 | BP-2023-24-359 | 24/11/2023 | 24/11/2023 | WBSEDCL | 4.07 | 0 | 0 | 0
4 | PURBA MEDINIPUR | Ramnagar-I | Midnapore Mechanical | GHANTA SHALA AND IT'S ADJOINING MOUJAS PWSS | SM/14456 | New | Quotation for new service connection at T/W-2 of Ghantashala ws scheme under MMD PHE DTE, Ref Application no-2004577503, Con ID-204203251 |  |  | BILL/03568/2023-2024 | BP-2023-24-651 | 09/02/2024 | 09/02/2024 | WBSEDCL | 8.39 | 0 | 0 | 0
5 | PURBA MEDINIPUR | Ramnagar-I | Midnapore Mechanical | GHANTA SHALA AND IT'S ADJOINING MOUJAS PWSS | SM/14456 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for GHANTA SHALA AND IT'S ADJOINING MOUJAS, Block ¿ Ramnagar I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division | ORD/001708/2022-2023 | 593/W/MMD | 20/03/2023 | 02/03/2025 | ASHUTOSH DAS & CO. | 21.53 | 0 | 0 | 80
6 | PURBA MEDINIPUR | Ramnagar-I | Tamluk Division | GHANTA SHALA AND IT'S ADJOINING MOUJAS PWSS | SM/14456 | New | Sinking of Tube Well ,Construction of Pump House ,100 cum OHR (Intze type with pile foundation), Rising main, Laying distribution pipe line, Boundary Wall, Soil investigation & Accommodate FHTC (672 nos) under JJM with allied work including 02(two) Years Operation & Maintenance of GHANTA SHALA PWSS within Ramnagar-I Block under Digha Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000350/2023-2024 | 852/TD | 31/05/2023 | 26/12/2025 | GHOSH CONSTRUCTION | 288.84 | 0 | 0 | 75
Total | [13 empty] | 353.56 | 0 | 0