## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR | Potashpur-I | Midnapore Mechanical | KULRAKHI AND IT'S ADJOINING MOUJAS PWSS | SM/14671 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for KULRAKHI AND IT'S ADJOINING MOUJAS, Block ¿ Potashpur I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001706/2022-2023 | 592/W/MMD | 20/03/2023 | 16/09/2023 | ASHUTOSH DAS & CO. | 21.53 | 0 | 0 | 0
2 | PURBA MEDINIPUR | Potashpur-I | Tamluk Division | KULRAKHI AND IT'S ADJOINING MOUJAS PWSS | SM/14671 | New | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House & Providing Functional Household Tap Connection (61964 Nos) For 38 nos Pipe water supply Scheme including two years Operation & Maintainance within Patashpur-I, Patashpur-II , Egra-I and Deshapran Block Under Tamluk Division PHE Dte. Under Purba Medinipur District. | Assistant Engineer,Assistant Engineer, Headquaters | Junior Engineer | ORD/000677/2023-2024 | 2702/TD | 20/10/2023 | 30/03/2026 | MACKINTOSH BURN LIMITED | 19507.71 | 125.85 | 0.65 | 51
3 | PURBA MEDINIPUR | Potashpur-I | Tamluk Division | KULRAKHI AND IT'S ADJOINING MOUJAS PWSS | SM/14671 | New | Material Requisition To Resource Division |  |  | RTOR000143/2022-2023 | 2448/TD | 16/01/2023 | 16/01/2023 | Resource Division | 26.2 | 0 | 0 | 0
4 | PURBA MEDINIPUR | Potashpur-I | Midnapore Mechanical | KULRAKHI AND IT'S ADJOINING MOUJAS PWSS | SM/14671 | New | Quotation Bill for New Service connection at T/W NO-II Of KULRAKHI W/S Scheme under MMD, PHE, Dte. Block- PATASHPUR-I, WBSEDCL SUPPLY OFFICE: AMARSHI C.C.C. Ref. Memo No- 2004769788/QUOT/03 DT. 10-06-2024 MEMO NO: AMR/PHE/171 DT. 10-06-2024 Application NO- 2004769788 Application type-New connection Consumer Id- 204327232 |  |  | BILL/01280/2024-2025 | BP-2024-25-339 | 25/06/2024 | 25/06/2024 | WBSEDCL | 3.11 | 0 | 0 | 0
5 | PURBA MEDINIPUR | Potashpur-I | Midnapore Mechanical | KULRAKHI AND IT'S ADJOINING MOUJAS PWSS | SM/14671 | New | Quotation Bill for New Service connection at T/W NO-I Of KULRAKHI W/S Scheme under MMD, PHE, Dte. Block- POTASHPUR-I, WBSEDCL SUPPLY OFFICE: AMARSI C.C.C. Ref. Memo No- 2004743601/QUOT/03 DT. 20-05-2024 Application NO- 2004743601 Application type-New connection Consumer Id- 204312616 |  |  | BILL/01204/2024-2025 | BP-2024-25-322 | 24/06/2024 | 24/06/2024 | WBSEDCL | 5.12 | 0 | 0 | 0
6 | PURBA MEDINIPUR | Potashpur-I | Tamluk Division | KULRAKHI AND IT'S ADJOINING MOUJAS PWSS | SM/14671 | New | Material Requisition To Resource Division |  |  | RTOR000030/2024-2025 | 1634/TD | 18/06/2025 | 18/06/2025 | Resource Division | 6.41 | 0 | 0 | 0
Total | [13 empty] | 19570.07 | 125.85 | 0.64