## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR | Potashpur-I | Tamluk Division | CHISTIPUR AND ADJOINING MOUJAS | SM/14672 | New | Material Requisition To Resource Division |  |  | RTOR000321/2022-2023 | 2994/TD | 27/02/2023 | 27/02/2023 | Resource Division | 17.01 | 0 | 0 | 0
2 | PURBA MEDINIPUR | Potashpur-I | Tamluk Division | CHISTIPUR AND ADJOINING MOUJAS | SM/14672 | New | Schedule for Preparation of design based on soil test report and submission of drawing of foundation for construction of 250 cum RCC OHR at Chistipur PWSS at Patashpur-I Block under Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000174/2024-2025 | 2086/TD | 24/06/2024 | 04/07/2024 | ASTER CONSULTANCY | 0.95 | 0.95 | 100 | 100
3 | PURBA MEDINIPUR | Potashpur-I | Midnapore Mechanical | CHISTIPUR AND ADJOINING MOUJAS | SM/14672 | New | Quotation Bill for New Service connection at T/W NO-II Of CHISTIPUR W/S Scheme under MMD, PHE, Dte. Block- POTASHPUR-I, WBSEDCL SUPPLY OFFICE: AMARSHI C.C.C. Ref. Memo No-2004835430/QUOT/03 DT. 26-07-2024 Application NO- 2004835430 MEMO NO: AMR/PHE/280 DT.26/7/2024 Application type-New connection Consumer Id- 204365756 |  |  | BILL/01859/2024-2025 | BP-2024-25-540 | 07/08/2024 | 07/08/2024 | WBSEDCL | 5.03 | 0 | 0 | 0
4 | PURBA MEDINIPUR | Potashpur-I | Midnapore Mechanical | CHISTIPUR AND ADJOINING MOUJAS | SM/14672 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for CHISTIPUR AND ITS ADJOINING MOUJAS, Block ¿ Potashpur I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/002041/2022-2023 | 949/W/MMD | 28/03/2023 | 31/08/2025 | M/S B.M. ELECTRICAL | 22.78 | 0 | 0 | 62
Total | [13 empty] | 45.78 | 0.95 | 2.08