## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR | Contai-I | Midnapore Mechanical | KASHI BHUIANBAR AND IT'S ADJOINING MOUJAS | SM/14673 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for KASHI BHUIANBAR AND IT'S ADJOINING MOUJAS, Block ¿ Contai I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division | ORD/001702/2022-2023 | 591/W/MMD | 20/03/2023 | 16/09/2023 | S.S.GHORAI | 21.58 | 13.15 | 60.92 | 62
2 | PURBA MEDINIPUR | Contai-I | Tamluk Division | KASHI BHUIANBAR AND IT'S ADJOINING MOUJAS | SM/14673 | New | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House & Providing Functional Household Tap Connection (32862 Nos), including 2 years Operation & Maintenance For 21 nos Pipe Water Supply Scheme within MOYNA AND CONTAI -I Block Under Tamluk Division PHE Dte. Under Purba Medinipur District. | Assistant Engineer | Junior Engiener,Junior Engineer | ORD/000538/2023-2024 | 1937/TD | 16/08/2023 | 28/03/2026 | MACKINTOSH BURN LIMITED | 10310.59 | 173.08 | 1.68 | 75
3 | PURBA MEDINIPUR | Contai-I | Tamluk Division | KASHI BHUIANBAR AND IT'S ADJOINING MOUJAS | SM/14673 | New | Material Requisition To Resource Division |  |  | RTOR000177/2022-2023 | 2398/TD | 16/01/2023 | 16/01/2023 | Resource Division | 34.37 | 0 | 0 | 0
4 | PURBA MEDINIPUR | Contai-I | Tamluk Division | KASHI BHUIANBAR AND IT'S ADJOINING MOUJAS | SM/14673 | New | Material Requisition To Resource Division |  |  | RTOR000091/2024-2025 | 2964/TD | 12/09/2024 | 12/09/2024 | Resource Division | 3.78 | 0 | 0 | 0
5 | PURBA MEDINIPUR | Contai-I | Midnapore Mechanical | KASHI BHUIANBAR AND IT'S ADJOINING MOUJAS | SM/14673 | New | Quotation Bill for New Service connection at T/W NO-I Of KASHI BHUINABAR W/S Scheme under MMD, PHE, Dte. Block- CONTAI-I, WBSEDCL SUPPLY OFFICE: CONTAI C.C.C. Ref. Memo No- 2004804684/QUOT/03 DT. 03-07-2024 Application NO- 2004804684 Application type-New connection Consumer Id- 204347452 |  |  | BILL/01468/2024-2025 | BP-2024-25-417 | 15/07/2024 | 15/07/2024 | WBSEDCL | 0.51 | 0 | 0 | 0
6 | PURBA MEDINIPUR | Contai-I | Tamluk Division | KASHI BHUIANBAR AND IT'S ADJOINING MOUJAS | SM/14673 | New | Preparation of design based on soil test report and submission of drawing of foundation for construction of 100 cum RCC OHR at KASHIBHUIAN BAR PWSS at Contai-I Block within Contai Sub-Division under Tamluk Division, PHE Dte. | Assistant Engineer |  | ORD/000608/2024-2025 | 189/CSD | 27/01/2025 | 11/02/2025 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.95 | 0 | 0 | 0
7 | PURBA MEDINIPUR | Contai-I | Midnapore Mechanical | KASHI BHUIANBAR AND IT'S ADJOINING MOUJAS | SM/14673 | New | Quotation Bill for New Service connection at T/W NO-II Of KASHI BHUNIABAR W/S Scheme under MMD, PHE, Dte. Block-CONTAI-I, WBSEDCL SUPPLY OFFICE: CONTAI C.C.C. Ref. Memo No- 2005078216/QUOT/03 DT. 07-02-2025 Application NO- 2005078216 Application type-New connection Consumer Id- 204522790 |  |  | BILL/04275/2024-2025 | C032555241732 | 17/03/2025 | 17/03/2025 | WBSEDCL | 12.48 | 0 | 0 | 0
Total | [13 empty] | 10384.27 | 186.22 | 1.79