## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR | Tamluk | Midnapore Mechanical | SATKALUA AND IT'S ADJOINING MOUJAS PWSS | SM/14695 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for SATKALUA AND IT'S ADJOINING MOUJAS, Block ¿ Tamluk, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/001716/2022-2023 | 595/W/MMD | 20/03/2023 | 16/09/2023 | INDIA ENTERPRISE | 21.62 | 10.61 | 49.09 | 35
2 | PURBA MEDINIPUR | Tamluk | Tamluk Division | SATKALUA AND IT'S ADJOINING MOUJAS PWSS | SM/14695 | New | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House & Boundary Wall, Providing Functional Household Tap Connection (1277 Nos), including 2 years Operation & Maintenance For Satkalua, Uttar Sautanchak, Pipe Water Supply Scheme within TAMLUK Block Under Tamluk Division PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000218/2023-2024 | 449/TD | 04/05/2023 | 01/04/2025 | TARUN KOLEY | 549.23 | 58.44 | 10.64 | 75
3 | PURBA MEDINIPUR | Tamluk | Tamluk Division | SATKALUA AND IT'S ADJOINING MOUJAS PWSS | SM/14695 | New | Material Requisition To Resource Division |  |  | RTOR000218/2022-2023 | 2673/TD | 06/02/2023 | 06/02/2023 | Resource Division | 19.08 | 0 | 0 | 0
4 | PURBA MEDINIPUR | Tamluk | Midnapore Mechanical | SATKALUA AND IT'S ADJOINING MOUJAS PWSS | SM/14695 | New | Satkalua W/S scheme H/W site. Application No.-2004547137 Ref.-204177910 |  |  | BILL/03302/2023-2024 | BP-2023-24-548 | 15/01/2024 | 15/01/2024 | WBSEDCL | 4.11 | 0 | 0 | 0
Total | [13 empty] | 594.04 | 69.06 | 11.62