## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR | Tamluk | Tamluk Division | UTTAR SAUTANCHAK Piped Water Supply Scheme. | SM/14741 | New | Material Requisition To Resource Division |  |  | RTOR000220/2022-2023 | 2674/TD | 06/02/2023 | 06/02/2023 | Resource Division | 13.79 | 0 | 0 | 0
2 | PURBA MEDINIPUR | Tamluk | Midnapore Mechanical | UTTAR SAUTANCHAK Piped Water Supply Scheme. | SM/14741 | New | New service connection at Uttar Sautanchak water supply scheme tube well no.-II Tamluk CCC Block-Tamluk Application No.-2004785533 Consumer ID.-204336033 Date.-21-06-2024 |  |  | BILL/01329/2024-2025 | BP-2024-25-356 | 01/07/2024 | 01/07/2024 | WBSEDCL | 2.93 | 0 | 0 | 0
3 | PURBA MEDINIPUR | Tamluk | Midnapore Mechanical | UTTAR SAUTANCHAK Piped Water Supply Scheme. | SM/14741 | New | Quotation bill for Uttat Sautanchak Water Supply scheme H/W site. Quotation Bill Date.-20/03/2024 Tamluk Block Tamluk CCC Application No.-2004648593 Ref. ID-204250592 |  |  | BILL/04735/2023-2024 | BP-2023-24-919 | 28/03/2024 | 28/03/2024 | WBSEDCL | 0.87 | 0 | 0 | 0
4 | PURBA MEDINIPUR | Tamluk | Midnapore Mechanical | UTTAR SAUTANCHAK Piped Water Supply Scheme. | SM/14741 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for UTTAR SAUTANCHAK PWSS, Block ¿ Tamluk, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/002038/2022-2023 | 946/W/MMD | 28/03/2023 | 16/03/2025 | M/S. S.R. ENTERPRISE | 21.55 | 12.49 | 57.97 | 75
5 | PURBA MEDINIPUR | Tamluk | Tamluk Division | UTTAR SAUTANCHAK Piped Water Supply Scheme. | SM/14741 | New | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House & Boundary Wall, Providing Functional Household Tap Connection (1277 Nos), including 2 years Operation & Maintenance For Satkalua, Uttar Sautanchak, Pipe Water Supply Scheme within TAMLUK Block Under Tamluk Division PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000218/2023-2024 | 449/TD | 04/05/2023 | 01/04/2025 | TARUN KOLEY | 549.23 | 93.52 | 17.03 | 75
Total | [13 empty] | 588.37 | 106.01 | 18.02