## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR | Ramnagar-II | Tamluk Division | DAKSHIN KALYANPUR AND IT'S ADJOINING MOUJAS PWSS | SM/14745 | New | Material Requisition To Resource Division |  |  | RTOR000304/2022-2023 | 3001/TD | 27/02/2023 | 27/02/2023 | Resource Division | 9.75 | 0 | 0 | 0
2 | PURBA MEDINIPUR | Ramnagar-II | Midnapore Mechanical | DAKSHIN KALYANPUR AND IT'S ADJOINING MOUJAS PWSS | SM/14745 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for DAKSHIN KALYANPUR AND IT'S ADJOINING MOUJAS PWSS, Block ¿ Ramnagar II, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division | ORD/001749/2022-2023 | 604/W/MMD | 20/03/2023 | 16/09/2023 | KRISHNA ENGINEERING | 11.95 | 0 | 0 | 45
3 | PURBA MEDINIPUR | Ramnagar-II | Tamluk Division | DAKSHIN KALYANPUR AND IT'S ADJOINING MOUJAS PWSS | SM/14745 | New | Preparation of design based on soil test report and submission of drawing of foundation for construction of 50 cum RCC OHR at Dakshin Kalyanpur PWSS at Ramnagar-II Block under Tamluk Division,PHE Dte. | Assistant Engineer |  | ORD/001049/2023-2024 | 379/TD | 29/01/2024 | 08/02/2024 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.95 | 0 | 0 | 100
4 | PURBA MEDINIPUR | Ramnagar-II | Tamluk Division | DAKSHIN KALYANPUR AND IT'S ADJOINING MOUJAS PWSS | SM/14745 | New | Material Requisition To Resource Division |  |  | RTOR000126/2023-2024 | 132/TD | 05/01/2024 | 05/01/2024 | Resource Division | 1.45 | 0 | 0 | 0
5 | PURBA MEDINIPUR | Ramnagar-II | Midnapore Mechanical | DAKSHIN KALYANPUR AND IT'S ADJOINING MOUJAS PWSS | SM/14745 | New | Quotation Bill for New Service connection at T/W NO-II Of DAKSHIN KALYANPUR W/S Scheme under MMD, PHE, Dte. Block- RAMANAGR-II, WBSEDCL SUPPLY OFFICE: PICHABANI C.C.C. Ref. Memo No- 2004671005/QUOT/03 DT. 05-04-2024 Application NO- 2004671005 Application type-New connection Consumer Id- 204268105 |  |  | BILL/00297/2024-2025 | BP-2024-25-47 | 18/04/2024 | 18/04/2024 | WBSEDCL | 2.16 | 0 | 0 | 0
6 | PURBA MEDINIPUR | Ramnagar-II | Tamluk Division | DAKSHIN KALYANPUR AND IT'S ADJOINING MOUJAS PWSS | SM/14745 | New | Sinking of Tube Well, Laying distribution pipe line, Pump House, Boundary Wall soil investigation, 50 Cum OHR & Accommodate FHTC ( 236 Nos) under JJM with allied work for DAKSHIN KALYANPUR & Its Adjoining Mouzas Water Supply Scheme within Ramnagar-II Block under Digha Sub-Division of Tamluk Division , PHED , Purba Medinipur | Assistant Engineer | Junior Engineer | ORD/000521/2023-2024 | 1758/TD | 01/08/2023 | 01/12/2025 | PREMANANDA ROY BISWAS | 164.16 | 0 | 0 | 40
7 | PURBA MEDINIPUR | Ramnagar-II | Tamluk Division | DAKSHIN KALYANPUR AND IT'S ADJOINING MOUJAS PWSS | SM/14745 | New | Drum Sheet walling, road restoration for distribution pipe line( for FHTC) & Accommodate FHTC (80 Nos) under JJM with allied work for Dakshin Kalyanpur PWSS within Ramnagar-II Block under Digha Sub-Division of Tamluk Division , PHED , Purba Medinipur | Assistant Engineer |  | ORD/000423/2024-2025 | 3474/TD | 06/11/2024 | 06/12/2024 | VENUS ENGINEERS CO-OPERATIVE SOCIETY LTD. | 20.7 | 0 | 0 | 0
Total | [13 empty] | 211.12 | 0 | 0