## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR | Deshopran | Midnapore Mechanical | MAHISHAGOT AND IT'S ADJOINING MOUJAS PWSS | SM/14749 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for MAHISHAGOT AND IT'S ADJOINING MOUJAS, Block ¿ Deshopran, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division | ORD/001737/2022-2023 | 601/W/MMD | 20/03/2023 | 16/09/2023 | SHAKEEL KHAN | 11.98 | 0 | 0 | 0
2 | PURBA MEDINIPUR | Deshopran | Tamluk Division | MAHISHAGOT AND IT'S ADJOINING MOUJAS PWSS | SM/14749 | New | Material Requisition To Resource Division |  |  | RTOR000213/2022-2023 | 2408/TD | 16/01/2023 | 16/01/2023 | Resource Division | 13.74 | 0 | 0 | 0
3 | PURBA MEDINIPUR | Deshopran | Tamluk Division | MAHISHAGOT AND IT'S ADJOINING MOUJAS PWSS | SM/14749 | New | Material Requisition To Resource Division |  |  | RTOR000088/2024-2025 | 2966/TD | 12/09/2024 | 12/09/2024 | Resource Division | 2.62 | 0 | 0 | 0
4 | PURBA MEDINIPUR | Deshopran | Tamluk Division | MAHISHAGOT AND IT'S ADJOINING MOUJAS PWSS | SM/14749 | New | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Head work site pipe connection, Rigid Pavement , Pump House & Boundry wall, Providing Functional Household Tap Connection (3145 Nos), including 2 years Operation & Maintenance For 4 nos Pipe Water Supply Scheme within Deshpran, Contai I &Contai III Block Under Tamluk Division PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000496/2023-2024 | 1674/TD | 25/07/2023 | 09/07/2026 | HALDIA DEVELOPMENT CONSTRUCTION | 1173.36 | 0 | 0 | 30
5 | PURBA MEDINIPUR | Deshopran | Midnapore Mechanical | MAHISHAGOT AND IT'S ADJOINING MOUJAS PWSS | SM/14749 | New | Quotation Bill for New Service connection at T/W NO-I Of MAHISHAGOAT W/S Scheme under MMD, PHE, Dte. Block- CONTAI-II, WBSEDCL SUPPLY OFFICE: MUKUNDAPUR C.C.C. Ref. Memo No- 2004965980/QUOT/03 DT. 22-11-2024 Application NO- 2004965980 Application type-New connection Consumer Id- 204446012 |  |  | BILL/03364/2024-2025 | C122421449766 | 16/12/2024 | 16/12/2024 | WBSEDCL | 7.31 | 0 | 0 | 0
6 | PURBA MEDINIPUR | Deshopran | Midnapore Mechanical | MAHISHAGOT AND IT'S ADJOINING MOUJAS PWSS | SM/14749 | New | Quotation Bill for New Service connection at T/W NO-II Of MAHISHAGOAT W/S Scheme under MMD, PHE, Dte. Block- CONTAI-II, WBSEDCL SUPPLY OFFICE: MUKUNDAPUR C.C.C. Ref. Memo No- 2004963932/QUOT/03 DT. 22-11-2024 Application NO- 2004963932 Application type-New connection Consumer Id- 204444763 |  |  | BILL/03363/2024-2025 | C122421452693 | 16/12/2024 | 16/12/2024 | WBSEDCL | 7.32 | 0 | 0 | 0
Total | [13 empty] | 1216.32 | 0 | 0