## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Tamluk Division | Piped Water Supply Scheme for Chirulia-Chatla Zone-3 | SM/14836 | Augmentation | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Chirulia Chatla Water Supply Scheme (Zone-III) under Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000495/2022-2023 | 1931./TD | 28/11/2022 | 18/12/2022 | ASTER CONSULTANCY | 3.46 | 3.46 | 100 | 100
2 | PURBA MEDINIPUR |  | Tamluk Division | Piped Water Supply Scheme for Chirulia-Chatla Zone-3 | SM/14836 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000091/2023-2024 | 2994/TD | 29/11/2023 | 29/11/2023 | Resource Division | 1.29 | 0 | 0 | 0
3 | PURBA MEDINIPUR |  | Tamluk Division | Piped Water Supply Scheme for Chirulia-Chatla Zone-3 | SM/14836 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000034/2023-2024 | 2063/TD | 28/08/2023 | 28/08/2023 | Resource Division | 13.54 | 0 | 0 | 0
4 | PURBA MEDINIPUR |  | Midnapore Mechanical | Piped Water Supply Scheme for Chirulia-Chatla Zone-3 | SM/14836 | Augmentation | Quotation for new service connection at Zone-III,TW-II of Chirulia Chatla ws scheme under MMD, PHE Dte. Block-Egra-I, Chopalia CCC. App. no-2004635402, Con ID-204242995 |  |  | BILL/04742/2023-2024 | Bp-2023-24-915 | 28/03/2024 | 28/03/2024 | WBSEDCL | 3.69 | 0 | 0 | 0
5 | PURBA MEDINIPUR |  | Midnapore Mechanical | Piped Water Supply Scheme for Chirulia-Chatla Zone-3 | SM/14836 | Augmentation | Chirulia Chatla W/S scheme Zone-III, T/W-I Application.-2004553660 Ref.-204183515 |  |  | BILL/03362/2023-2024 | BP-2023-24-575 | 18/01/2024 | 18/01/2024 | WBSEDCL | 4.96 | 0 | 0 | 0
6 | PURBA MEDINIPUR |  | Midnapore Mechanical | Piped Water Supply Scheme for Chirulia-Chatla Zone-3 | SM/14836 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Piped Water Supply Scheme for Chirulia-Chatla Zone-3 Egra I Block under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division | ORD/001984/2022-2023 | 892/W/MMD | 27/03/2023 | 31/08/2025 | SHREE BISHNU CONSTRUCTION | 23.68 | 0 | 0 | 52
7 | PURBA MEDINIPUR |  | Tamluk Division | Piped Water Supply Scheme for Chirulia-Chatla Zone-3 | SM/14836 | Augmentation | Sinking of Tube Well, Laying distribution pipe line, Pump House, Boundary Wall soil investigation, 250 Cum OHR & Accommodate FHTC ( 210 Nos) under JJM with allied work for Chirulia-Chatla (Zone-III) PWSS within Egra-I Block under Digha Sub-Division of Tamluk Division , PHED , Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000407/2023-2024 | 1089/TD | 08/06/2023 | 30/06/2025 | AJIT KUMAR SOM | 233.68 | 78.46 | 33.57 | 85
Total | [13 empty] | 284.31 | 81.91 | 28.81