## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Tamluk Division | Different Works for Providing Functional Household TAP Connection (FHTC) by Augmentation of Digha (Central) Water Supply Scheme. | SM/14837 | Augmentation | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Digha Water Supply Scheme (Central Zone) under Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000444/2021-2022 | 1665/TD | 24/01/2022 | 13/02/2022 | HORIZEN | 3.52 | 3.46 | 98.21 | 100
2 | PURBA MEDINIPUR |  | Tamluk Division | Different Works for Providing Functional Household TAP Connection (FHTC) by Augmentation of Digha (Central) Water Supply Scheme. | SM/14837 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000054/2023-2024 | 2077/TD | 28/08/2023 | 28/08/2023 | Resource Division | 38.59 | 0 | 0 | 0
3 | PURBA MEDINIPUR |  | Tamluk Division | Different Works for Providing Functional Household TAP Connection (FHTC) by Augmentation of Digha (Central) Water Supply Scheme. | SM/14837 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000066/2023-2024 | 2642/TD | 13/10/2023 | 13/10/2023 | Resource Division | 12.75 | 0 | 0 | 0
4 | PURBA MEDINIPUR |  | Midnapore Mechanical | Different Works for Providing Functional Household TAP Connection (FHTC) by Augmentation of Digha (Central) Water Supply Scheme. | SM/14837 | Augmentation | Hiring of inspection vehicle for supervision & monitoring of different on-going piped water supply scheme for covering Contai Sub-Division and its adjacent Sub-Division under the Dist. of Purba Medinipur under Jal Jeevan Mission programe. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division.,Sri Ujjal Kumar Dey, JE/Haldia Electrical Sub-Division. | ORD/001951/2022-2023 | 101/HESD | 27/02/2023 | 30/08/2023 | S.S.GHORAI | 0.9 | 0 | 0 | 53
5 | PURBA MEDINIPUR |  | Midnapore Mechanical | Different Works for Providing Functional Household TAP Connection (FHTC) by Augmentation of Digha (Central) Water Supply Scheme. | SM/14837 | Augmentation | Providing and Installation of electromechanical equipments for Different Works for Providing Functional Household TAP Connection (FHTC) by Augmentation of Digha (Central) Water Supply Scheme in Block Ramnagar I under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division | ORD/000071/2023-2024 | 1241/W/MMD | 28/04/2023 | 25/10/2023 | SOUMEN ELECTRIC | 33.56 | 33.15 | 98.8 | 100
6 | PURBA MEDINIPUR |  | Midnapore Mechanical | Different Works for Providing Functional Household TAP Connection (FHTC) by Augmentation of Digha (Central) Water Supply Scheme. | SM/14837 | Augmentation | Quotation for new service connection at TW-II of Digha Central zone under MMD, PHE Dte, Block-Ramnagar-I, DIGHA CCC Application no-2004812648 CON ID-204351925 |  |  | BILL/01585/2024-2025 | C072438486724 | 23/07/2024 | 23/07/2024 | WBSEDCL | 0.71 | 0 | 0 | 0
7 | PURBA MEDINIPUR |  | Midnapore Mechanical | Different Works for Providing Functional Household TAP Connection (FHTC) by Augmentation of Digha (Central) Water Supply Scheme. | SM/14837 | Augmentation | Quotation for new service connection at T/W-III of Digha Central zone under MMD,PHE DTE, Block-Ramnagar-I, DIGHA CCC Application no-2004812635 CON ID-204351924 |  |  | BILL/01584/2024-2025 | C072438487551 | 23/07/2024 | 23/07/2024 | WBSEDCL | 0.43 | 0 | 0 | 0
8 | PURBA MEDINIPUR |  | Tamluk Division | Different Works for Providing Functional Household TAP Connection (FHTC) by Augmentation of Digha (Central) Water Supply Scheme. | SM/14837 | Augmentation | Sinking of Tube Well ,Laying distribution pipe line, Pump House , Boundary Wall soil investigation , 300 cum OHR (Intze type with pile foundation) & Accommodate FHTC (2069 nos) under JJM with allied work for Digha Augmentation (Central Zone) PWSS within Ramnagar-I Block including supply of all labour & materials under Digha Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000612/2023-2024 | 2271/TD | 05/09/2023 | 21/11/2025 | ORIENT CONSTRUCTION | 477.25 | 166.99 | 34.99 | 22
Total | [13 empty] | 567.7 | 203.59 | 35.86