## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Tamluk Division | Different Works for Providing Functional Household TAP Connection (FHTC) by Augmentation of Digha (Central) Water Supply Scheme. | SM/14837 | Augmentation | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Digha Water Supply Scheme (Central Zone) under Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000444/2021-2022 | 1665/TD | 24/01/2022 | 13/02/2022 | HORIZEN | 3.52 | 3.46 | 98.21 | 100
2 | PURBA MEDINIPUR |  | Tamluk Division | Different Works for Providing Functional Household TAP Connection (FHTC) by Augmentation of Digha (Central) Water Supply Scheme. | SM/14837 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000054/2023-2024 | 2077/TD | 28/08/2023 | 28/08/2023 | Resource Division | 38.59 | 0 | 0 | 0
3 | PURBA MEDINIPUR |  | Tamluk Division | Different Works for Providing Functional Household TAP Connection (FHTC) by Augmentation of Digha (Central) Water Supply Scheme. | SM/14837 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000066/2023-2024 | 2642/TD | 13/10/2023 | 13/10/2023 | Resource Division | 12.75 | 0 | 0 | 0
4 | PURBA MEDINIPUR |  | Midnapore Mechanical | Different Works for Providing Functional Household TAP Connection (FHTC) by Augmentation of Digha (Central) Water Supply Scheme. | SM/14837 | Augmentation | Providing and Installation of electromechanical equipments for Different Works for Providing Functional Household TAP Connection (FHTC) by Augmentation of Digha (Central) Water Supply Scheme in Block Ramnagar I under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division | ORD/000071/2023-2024 | 1241/W/MMD | 28/04/2023 | 25/10/2023 | SOUMEN ELECTRIC | 33.56 | 33.15 | 98.8 | 100
5 | PURBA MEDINIPUR |  | Midnapore Mechanical | Different Works for Providing Functional Household TAP Connection (FHTC) by Augmentation of Digha (Central) Water Supply Scheme. | SM/14837 | Augmentation | Quotation for new service connection at TW-II of Digha Central zone under MMD, PHE Dte, Block-Ramnagar-I, DIGHA CCC Application no-2004812648 CON ID-204351925 |  |  | BILL/01585/2024-2025 | C072438486724 | 23/07/2024 | 23/07/2024 | WBSEDCL | 0.71 | 0 | 0 | 0
6 | PURBA MEDINIPUR |  | Midnapore Mechanical | Different Works for Providing Functional Household TAP Connection (FHTC) by Augmentation of Digha (Central) Water Supply Scheme. | SM/14837 | Augmentation | Quotation for new service connection at T/W-III of Digha Central zone under MMD,PHE DTE, Block-Ramnagar-I, DIGHA CCC Application no-2004812635 CON ID-204351924 |  |  | BILL/01584/2024-2025 | C072438487551 | 23/07/2024 | 23/07/2024 | WBSEDCL | 0.43 | 0 | 0 | 0
7 | PURBA MEDINIPUR |  | Tamluk Division | Different Works for Providing Functional Household TAP Connection (FHTC) by Augmentation of Digha (Central) Water Supply Scheme. | SM/14837 | Augmentation | Sinking of Tube Well ,Laying distribution pipe line, Pump House , Boundary Wall soil investigation , 300 cum OHR (Intze type with pile foundation) & Accommodate FHTC (2069 nos) under JJM with allied work for Digha Augmentation (Central Zone) PWSS within Ramnagar-I Block including supply of all labour & materials under Digha Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000612/2023-2024 | 2271/TD | 05/09/2023 | 21/11/2025 | ORIENT CONSTRUCTION | 477.25 | 166.99 | 34.99 | 22
8 | PURBA MEDINIPUR |  | Midnapore Mechanical | Different Works for Providing Functional Household TAP Connection (FHTC) by Augmentation of Digha (Central) Water Supply Scheme. | SM/14837 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Newly sunk Tube well at Augmentation of Digha ( Central Zone) Water supply scheme, Ramnagar - I block, District - Purba Medinipur under Midnapore Mechanical Division P.H.E. Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division | ORD/002718/2023-2024 | 1063/W/MMD | 14/03/2024 | 30/04/2025 | S.S.GHORAI | 29.05 | 17.81 | 61.33 | 100
9 | PURBA MEDINIPUR |  | Tamluk Division | Different Works for Providing Functional Household TAP Connection (FHTC) by Augmentation of Digha (Central) Water Supply Scheme. | SM/14837 | Augmentation | Construction of boundary wall, repairing & renovation of Switch Room , existing boundary wall, OHR 250 cum. capacity 20 m height, & Accommodate FHTC (145 Nos) under JJM with allied work for Digha Augmentation (Central Zone ) Water Supply Scheme under Digha Sub Division of Tamluk Division, PHE Dte. Purba Medinipur . | Assistant Engineer | Junior Engineer | ORD/000322/2024-2025 | 3218/TD | 01/10/2024 | 15/11/2024 | ONKAR ENTERPRISE | 50.13 | 0 | 0 | 100
Total | [13 empty] | 645.97 | 221.41 | 34.28